## Sheet1
Process | Priority | SOW (hrs) | 2022-02-04 | 2022-02-11 | 2022-02-18 | 2022-02-25 | 2022-03-04 | 2022-03-11 | 2022-03-18 | 2022-03-25 | 2022-04-01 | 2022-04-08 | 2022-04-15 | 2022-04-22 | 2022-04-29 | 2022-05-06 | 2022-05-13 | 2022-05-20
SCHOOL MANAGEMENT |  |  | 2022-04-15: Complete Delivery of Phase 1
SCHOOL LIST | 2 | 20 | 2022-03-04: Defer to phase 2
SCHOOL ACTIVATION | 1 |  | 2022-02-18: Deliver BP
GRADE ACTIVATION | 2022-02-01 |  | 2022-03-04: Deliver BP
PROGRAMME ACTIVATION | 2022-02-01 |  | 2022-03-04: Deliver BP
SCHOOL DEACTIVATION | 2 | bar: 2022-02-04 to 2022-04-08
GRADE DEACTIVATION | 2 | bar: 2022-02-04 to 2022-04-08
CREATION OF SCHOOLS IN PROGRAMMES | 1 |  | 2022-02-18: Deliver BP
LEARNER MANAGEMENT
LEARNER IMPORT - DDD SCHOOLS (ALL SCHOOLS EXCL. WC) | 1 | 332 | 2022-02-18: Deliver BP
LEARNER IMPORT - CEMIS SCHOOLS (WC ONLY) | 1 |  | 2022-02-18: Deliver BP
LEARNER PROGRAMME REGISTRATON | 1 | 50 | 2022-02-18: Source API info
LEARNER ROLLOVER | 2 | bar: 2022-02-04 to 2022-04-08
LEARNER PROGRAMME / DW DE-REGISTRATION | 1
LEARNER PROGRAMME DATA - RE | 1 | 40 | 2022-02-18: Source API info
LEARNER PROGRAMME DATA - MATIFIC | 1 | 20 | 2022-02-18: Source API info
LEARNER PROGRAMME DATA - RL | 1 |  | 2022-02-25: Deliver BP
LEARNER PERFORMANCE DATA - DDD | 1 |  | 2022-02-25: Deliver BP
LEARNER ASSESSMENT (eQuiz) | 1 |  | 2022-03-04: Deliver BP
PEOPLE MANAGEMENT | 1 |  | 2022-03-11: Deliver BP
DATAMART | 1 |  | 2022-03-18: Deliver BP
Estimated no of work hours per week (2.5 resources) | 80 |  | 2022-02-18: Click
Silicon Overdrive SOW
Deliverables for discussion
|  |  |  | BP | Business Process