## 1. Introduction
Project Planning and Monitoring Tool
Purpose: This tool assists in organizing and monitoring project work.
Instructions: This tool can be used for planning, managing, and monitoring projects and will provide the user with a project Gantt chart, an issue log, and time-based progress reports. Begin by entering the basic project data in tab 3 and then start populating and updating the tasks and their progress where appropriate. For any issues that arise, track them in the issue log located on tab 4. Finally, on tab 5, enter the desired timeframe and a progress report will be produced. Important Notice: Although this tool is capable of advanced functions, keep in mind that this is a light project management tool working within the limitations of Microsoft Excel. Also pay close attention to any notices or warnings included within the individual tabs or cells.
Getting Started: Beginning with tab 2, use the worksheet tabs along the bottom of the spreadsheet screen. Some of the column headings in the sections include comments that offer additional instructions. Hover over the column headings to view these instructions.

## 2. Project Data
Project Data
Project Name | The Click Foundation AWS Migration and Modernization
Estimated Project Start Date | 2021-04-19
Estimated Project End Date | 2022-04-15
Project Owner | Gareth Bowers, Heinrich Du Plessis, Jaco Brits
Customer Project Team Members | Willem Boshoff, willem@clicklearning.org
Silicon Project Team Members | Gareth Bowers, CEO, gareth@overdrive.co.za Charlton Daniels, AWS Technical Specialist, charlton@overdrive.co.za Heinrich Du Plessis, AWS Senior Engineer, heinrich@overdrive.co.za Cole Barnard, AWS Project Manager, cole@overdrive.co.za Theodor Harmse, AWS Solutions Architect, theodor@overdrive.co.za Romano Moses, AWS Engineer, romano@overdrive.co.za Christopher Voges, Linux and AWS Engineer, christopher@overdrive.co.za Ashley Chamboko, AWS Sales Engineer, Ashley@overdrive.co.za Christine Gorgulho, Customer Support Manager, christine@overdrive.co.za Lenetia Plage, Service Delivery Manager, lenetia@overdrive.co.za Jessica Smith, Operations Manager, jessica@overdrive.co.za Ross Davie, Business Development Director, ross@overdrive.co.za
AWS Project Team Members
Project Stakeholders and Participants | 2. Holidays / Time Off Project
Name | Date | Holiday
Customer Team | 2020-03-21 | Human Rights Day
Silicon Team | 2020-04-10 | Good Friday
Customer and Silicon Team | 2020-04-13 | Family Day
Unassigned | 2020-04-27 | Freedom Day
| 2020-05-01 | Worker's Day
Willem Boshoff | 2020-06-16 | Youth Day
| 2020-08-09 | National Women's Day
Gareth Bowers | 2020-08-10 | Public Holiday
Charlton Daniels | 2020-09-24 | Heritage Day
Heinrich Du Plessis | 2020-12-16 | Day of Reconciliation
Cole Barnard | 2020-12-25 | Christmas Day
Theodor Harmse | 2020-12-26 | Day of Goodwill
Romano Moses
Christopher Voges
Dean Norman
Christine Gorgulho
Lenetia Plage
Jessica Smith
Ross Davie
Software Team
Note on B19: List all project participants and stakeholders. Include all project member names that will be actually involved with owning/implementing parts of the project. Feel free to insert multiple names of a team.
Note on D19: All dates in this list will not be made available in the project planning Gantt chart. Make sure that ranges are written out one date at a time. For example, if there is a week of non-project work, write out the five days as separate entries. Make sure to include only days that are not dedicated to the project as a whole. Remember, these dates will be blanked out completely.

## 3. Work Schedule
Work Schedule Monitoring
IMPORTANT NOTICE: It is very important that the following actions are followed: - Tasks must be entered with unique names. If task names are repeated, the data will not carry over correctly. Name each task differently. - Task Owner must be selected from the drop down menu. If unique names are entered, the report data will not carry over correctly. Do not attempt to insert or delete rows, as this will result in calculation errors throughout the tool. | [6 empty] | GANTT CHART LEGEND
Holiday / Vacation / No Work
Planned Project Work Day
Project Work Completed
COMPLETION STATUS LEGEND
Task Completed Ahead of Schedule
Task Completed Behind Schedule
Project Information | [6 empty] | Week 1 |  |  |  |  | Week 2 |  |  |  |  | Week 3 |  |  |  |  | Week 4 |  |  |  |  | Week 5 |  |  |  |  | Week 6 |  |  |  |  | Week 7 |  |  |  |  | Week 8 |  |  |  |  | Week 9 |  |  |  |  | Week 10 |  |  |  |  | Week 11 |  |  |  |  | Week 12 |  |  |  |  | Week 13 |  |  |  |  | Week 14 |  |  |  |  | Week 15 |  |  |  |  | Week 16 |  |  |  |  | Week 17 |  |  |  |  | Week 18 |  |  |  |  | Week 19 |  |  |  |  | Week 20 |  |  |  |  | Week 21 |  |  |  |  | Week 22 |  |  |  |  | Week 23 |  |  |  |  | Week 24 |  |  |  |  | Week 25 |  |  |  |  | Week 26 |  |  |  |  | Week 27 |  |  |  |  | Week 28 |  |  |  |  | Week 29 |  |  |  |  | Week 30 |  |  |  |  | Week 31 |  |  |  |  | Week 32 |  |  |  |  | Week 33 |  |  |  |  | Week 34 |  |  |  |  | Week 35 |  |  |  |  | Week 36 |  |  |  |  | Week 37 |  |  |  |  | Week 38 |  |  |  |  | Week 39 |  |  |  |  | Week 40 |  |  |  |  | Week 41 |  |  |  |  | Week 42 |  |  |  |  | Week 43 |  |  |  |  | Week 44 |  |  |  |  | Week 45 |  |  |  |  | Week 46 |  |  |  |  | Week 47 |  |  |  |  | Week 48 |  |  |  |  | Week 49 |  |  |  |  | Week 50 |  |  |  |  | Week 51 |  |  |  |  | Week 52 |  |  |  |  | Week 53 |  |  |  |  | Week 54
Task | Estimated Start Date | Estimated Completion Date | Task Owner (Must use drop-down menu) | Actual Start Date | Actual Completion Date | Dependencies and Prerequisites | 2021-04-19 |  |  |  |  | 2021-04-26 |  |  |  |  | 2021-05-03 |  |  |  |  | 2021-05-10 |  |  |  |  | 2021-05-17 |  |  |  |  | 2021-05-24 |  |  |  |  | 2021-05-31 |  |  |  |  | 2021-06-07 |  |  |  |  | 2021-06-14 |  |  |  |  | 2021-06-21 |  |  |  |  | 2021-06-28 |  |  |  |  | 2021-07-05 |  |  |  |  | 2021-07-12 |  |  |  |  | 2021-07-19 |  |  |  |  | 2021-07-26 |  |  |  |  | 2021-08-02 |  |  |  |  | 2021-08-09 |  |  |  |  | 2021-08-16 |  |  |  |  | 2021-08-23 |  |  |  |  | 2021-08-30 |  |  |  |  | 2021-09-06 |  |  |  |  | 2021-09-13 |  |  |  |  | 2021-09-20 |  |  |  |  | 2021-09-27 |  |  |  |  | 2021-10-04 |  |  |  |  | 2021-10-11 |  |  |  |  | 2021-10-18 |  |  |  |  | 2021-10-25 |  |  |  |  | 2021-11-01 |  |  |  |  | 2021-11-08 |  |  |  |  | 2021-11-15 |  |  |  |  | 2021-11-22 |  |  |  |  | 2021-11-29 |  |  |  |  | 2021-12-06 |  |  |  |  | 2021-12-13 |  |  |  |  | 2021-12-20 |  |  |  |  | 2021-12-27 |  |  |  |  | 2022-01-03 |  |  |  |  | 2022-01-10 |  |  |  |  | 2022-01-17 |  |  |  |  | 2022-01-24 |  |  |  |  | 2022-01-31 |  |  |  |  | 2022-02-07 |  |  |  |  | 2022-02-14 |  |  |  |  | 2022-02-21 |  |  |  |  | 2022-02-28 |  |  |  |  | 2022-03-07 |  |  |  |  | 2022-03-14 |  |  |  |  | 2022-03-21 |  |  |  |  | 2022-03-28 |  |  |  |  | 2022-04-04 |  |  |  |  | 2022-04-11 |  |  |  |  | 2022-04-18 |  |  |  |  | 2022-04-25
[7 empty] | 19 | 20 | 21 | 22 | 23 | 26 | 27 | 28 | 29 | 30 | 3 | 4 | 5 | 6 | 7 | 10 | 11 | 12 | 13 | 14 | 17 | 18 | 19 | 20 | 21 | 24 | 25 | 26 | 27 | 28 | 31 | 1 | 2 | 3 | 4 | 7 | 8 | 9 | 10 | 11 | 14 | 15 | 16 | 17 | 18 | 21 | 22 | 23 | 24 | 25 | 28 | 29 | 30 | 1 | 2 | 5 | 6 | 7 | 8 | 9 | 12 | 13 | 14 | 15 | 16 | 19 | 20 | 21 | 22 | 23 | 26 | 27 | 28 | 29 | 30 | 2 | 3 | 4 | 5 | 6 | 9 | 10 | 11 | 12 | 13 | 16 | 17 | 18 | 19 | 20 | 23 | 24 | 25 | 26 | 27 | 30 | 31 | 1 | 2 | 3 | 6 | 7 | 8 | 9 | 10 | 13 | 14 | 15 | 16 | 17 | 20 | 21 | 22 | 23 | 24 | 27 | 28 | 29 | 30 | 1 | 4 | 5 | 6 | 7 | 8 | 11 | 12 | 13 | 14 | 15 | 18 | 19 | 20 | 21 | 22 | 25 | 26 | 27 | 28 | 29 | 1 | 2 | 3 | 4 | 5 | 8 | 9 | 10 | 11 | 12 | 15 | 16 | 17 | 18 | 19 | 22 | 23 | 24 | 25 | 26 | 29 | 30 | 1 | 2 | 3 | 6 | 7 | 8 | 9 | 10 | 13 | 14 | 15 | 16 | 17 | 20 | 21 | 22 | 23 | 24 | 27 | 28 | 29 | 30 | 31 | 3 | 4 | 5 | 6 | 7 | 10 | 11 | 12 | 13 | 14 | 17 | 18 | 19 | 20 | 21 | 24 | 25 | 26 | 27 | 28 | 31 | 1 | 2 | 3 | 4 | 7 | 8 | 9 | 10 | 11 | 14 | 15 | 16 | 17 | 18 | 21 | 22 | 23 | 24 | 25 | 28 | 1 | 2 | 3 | 4 | 7 | 8 | 9 | 10 | 11 | 14 | 15 | 16 | 17 | 18 | 21 | 22 | 23 | 24 | 25 | 28 | 29 | 30 | 31 | 1 | 4 | 5 | 6 | 7 | 8 | 11 | 12 | 13 | 14 | 15 | 18 | 19 | 20 | 21 | 22 | 25 | 26 | 27 | 28 | 29
[7 empty] | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F
Proposal Planning Phase
Discuss, discover, analyze, and prioritize application and data centre resource portfolios for migration with the customer | 2021-04-19 | 2021-05-13 | Customer and Silicon Team | 2021-04-19 | 2021-05-13 | bar: 2021-04-19 19 M to 2021-05-10 13 T
Document discovered resources, dependencies, and usage data | 2021-04-19 | 2021-05-13 | Silicon Team | 2021-04-19 | 2021-05-13 | bar: 2021-04-19 19 M to 2021-05-10 13 T
Document a prioritized list of applications and workloads for migration | 2021-04-19 | 2021-05-13 | Silicon Team | 2021-04-19 | 2021-05-13 | bar: 2021-04-19 19 M to 2021-05-10 13 T
Assess and design an initial AWS account structure. Assess AWS Organizations or Landing Zone for suitability | 2021-04-19 | 2021-05-13 | Silicon Team | 2021-04-19 | 2021-05-13 | bar: 2021-04-19 19 M to 2021-05-10 13 T
Proposal Design Phase
Determine migration method – Re-host, Re-platform, Re-factor, Re-purchase, Retain, or Retire | 2021-05-13 | 2021-06-07 | Silicon Team | 2021-05-13 | 2021-06-07 | bar: 2021-05-10 13 T to 2021-06-07 7 M
Discuss with customer and specify migration target requirements (security, reliability, scaling, performance, monitoring, deployment automation, RTO, RPO etc.) | 2021-05-13 | 2021-06-07 | Silicon Team | 2021-05-13 | 2021-06-07 | bar: 2021-05-10 13 T to 2021-06-07 7 M
Create a Migration Proposal. Based on the above and the account structure defined in the Planning Phase, design the AWS Best Practice Architecture with architectural diagrams; address the requirements using the AWS Well-Architected Framework covering security, reliability, performance efficiency, cost optimization, and operations excellence. Create cost estimates using the AWS Pricing Calculator. Assess eligible AWS funding programs to access usage and or migration funding for the customer. Estimate project hours to deliver the project based on the Architecture and Project Scope. Evaluate and select migration tools or method. Document deliverables. | 2021-05-13 | 2021-06-07 | Silicon Team | 2021-05-13 | 2021-06-07 | bar: 2021-05-10 13 T to 2021-06-07 7 M
Project Proposal Authorisation Phase
Present and discuss the Proposal with the customer. Select and sign off the architecture, AWS pricing estimates, AWS Marketplace pricing estimates, AWS funding, scope, our professional services pricing estimates and timeline. Discuss the AWS Pricing Calculator limitations, security guidelines, cost optimization process and project planning phases. Present AWS account linking and CloudHealth benefits. Present Trend Cloud Conformity pricing. | 2021-06-07 | 2021-07-15 | Silicon Team | 2021-06-07 | 2021-07-15 | bar: 2021-06-07 7 M to 2021-07-12 15 T
Finalise the Proposal in discussion with the customer | 2021-06-07 | 2021-07-15 | Silicon Team | 2021-06-07 | 2021-07-15 | bar: 2021-06-07 7 M to 2021-07-12 15 T
Authorize AWS account linking and CloudHealth free of charge. | 2021-06-07 | 2021-07-15 | Customer Team | 2021-06-07 | 2021-07-15 | bar: 2021-06-07 7 M to 2021-07-12 15 T
Authorize Trend Cloud Conformity on an annual basis, billed monthly |  |  | Customer Team
Customer to initial all pages and sign the Proposal | 2021-07-15 | 2021-07-15 | Customer Team | 2021-07-15 | 2021-07-15 | bar: 2021-07-12 15 T
AWS Account Linking and Cost Optimization Reporting: Link account/s for cost and AWS credit benefits and setup CloudHealth reporting and alerting for rightsizing, alerting and cost optimization reporting.
Link your AWS account | 2021-07-15 | 2021-09-20 | Silicon Team | 2021-07-15 | 2021-09-20 | bar: 2021-07-12 15 T to 2021-09-20 20 M
Link your AWS account to CloudHealth | 2021-07-15 | 2021-09-20 | Silicon Team | 2021-07-15 | 2021-09-20 | bar: 2021-07-12 15 T to 2021-09-20 20 M
Setup automated CloudHealth reporting: Cost Optimisation Opportunities, Cloud Governance, Operational Monthly Savings, Security Risk Exposure, Rightsizing Recommendations, Reserved Instance reporting | 2021-07-15 | 2021-09-20 | Silicon Team | 2021-07-15 | 2021-09-20 | bar: 2021-07-12 15 T to 2021-09-20 20 M
Setup access to CloudHealth Console | 2021-07-15 | 2021-09-20 | Silicon Team | 2021-07-15 | 2021-09-20 | bar: 2021-07-12 15 T to 2021-09-20 20 M
Basic CloudHealth training | 2021-07-15 | 2021-09-20 | Silicon Team | 2021-07-15 | 2021-09-20 | bar: 2021-07-12 15 T to 2021-09-20 20 M
AWS Funding Application
Generate the AWS funding application documentation based on the finalised proposal authorized by the customer. Submit to appropriate AWS program | 2021-07-15 | 2021-09-20 | Silicon Team | 2021-07-15 | 2021-09-20 | bar: 2021-07-12 15 T to 2021-09-20 20 M
On AWS funding approval, update the Proposal the reflect the funding achieved. | 2021-09-20 | 2021-09-20 | Silicon Team | 2021-09-20 | 2021-09-20 | bar: 2021-09-20 20 M
Project Plan Phase
Generate the Project Plan including stakeholders and participants, work schedule and task owners | 2021-09-20 |  | Silicon Team
Refine and finalise the project plan in discussion |  |  | Customer and Silicon Team
Discovery Phase
Applying for Discovery Credits | 2021-08-23 | 2021-08-30 | Software Team | 2021-08-23 | 2021-08-30 | bar: 2021-08-23 23 M to 2021-08-30 30 M
Awarded Discovery Credits | 2021-09-15 | 2021-09-15 | Software Team | 2021-09-15 | 2021-09-15 | bar: 2021-09-13 15 W
Create 3 x PostgreSQL database and convert tables | 2021-09-15 | 2021-09-24 | Software Team | 2021-09-15 | 2021-10-20 | bar: 2021-09-13 15 W to 2021-09-20 24 F
Copy both React web portals and connect to the PostgreSQL databases | 2021-09-22 | 2021-10-20 | Software Team | 2021-09-22 | 2021-10-20 | bar: 2021-09-20 22 W to 2021-10-18 20 W
Investigating stored procedures (SP) behind the 2 portals | 2021-10-07 | 2021-10-29 | Software Team | 2021-10-07 | 2021-10-29 | bar: 2021-10-04 7 T to 2021-10-25 29 F
Investigating import / export processes - will replicate : DDD (26 Stored Procedures); School Import; CEMIS; Reading Eggs; Matific; Mathseeds; Quizzes | 2021-11-02 | 2021-12-10 | Software Team | 2021-11-02 | 2022-01-15 | bar: 2021-11-01 2 T to 2021-12-06 10 F
Testing roll-over in SQL | 2021-12-05 | 2021-12-10 | bar: 2021-12-06 6 M to 2021-12-06 10 F
Testing roll-over in PostgreSQL | 2021-12-05 | 2021-12-10 | bar: 2021-12-06 6 M to 2021-12-06 10 F
Final import from Gavin | 2021-12-10 | 2021-12-15 | bar: 2021-12-06 10 F to 2021-12-13 15 W
SOW - will modernise : DDD (26 Stored Procedures); School Import; CEMIS; Reading Eggs; Matific; Mathseeds; Quizzes | 2021-12-06 | 2021-12-15 | Software Team | 2022-01-10 | 2022-01-15 | End date will be a function of the Discovery | bar: 2021-12-06 6 M to 2021-12-13 15 W
DDD+CEMIS and Modernisation Phase | 2022-02-04
Automate current manual process : LearnerRegistrationCheck.SQL, if possible due to data consistency. | 2022-02-04 | 2022-03-04 | Software Team |  |  | 60 hrs | bar: 2022-01-31 4 F to 2022-02-28 4 F
Automate current manual process : TransferDW_Learner_Registrations.dtsx, if possible due to data consistency. | 2022-02-04 | 2022-03-04 | Software Team |  |  | 60 hrs | bar: 2022-01-31 4 F to 2022-02-28 4 F
Testing and rewriting 6 slow running queries | 2022-02-25 | 2022-03-11 | Software Team |  |  | 60 hrs | bar: 2022-02-21 25 F to 2022-03-07 11 F
Testing entire data import processes for DDD + CEMIS | 2022-03-11 | 2022-04-08 | Software Team |  |  | 80 hrs | bar: 2022-03-07 11 F to 2022-04-04 8 F
Documenting above item (data import processes) as runbooks | 2022-03-25 | 2022-04-08 | Software Team |  |  | 40 hrs | bar: 2022-03-21 25 F to 2022-04-04 8 F
Implement sFTP to S3 calling Lambda Step Functions calling SSIS (which calls PostgreSQL SP) (around 6 processes) |  |  | Software Team |  |  | 32 hrs
Reading Eggs Phase
API specification | 2022-02-04 | 2022-02-18 | Willem Boshoff |  |  | ? | bar: 2022-01-31 4 F to 2022-02-14 18 F
Rewrite SSIS script for use with PostgreSQL : Export_ReadingEggs.dtsx | 2022-02-18 | 2022-03-25 | Software Team | 2022-02-18 | 2022-03-25 | 30 hrs | bar: 2022-02-14 18 F to 2022-03-21 25 F
Testing complete import process | 2022-02-18 | 2022-03-25 | Software Team |  |  | 30 hrs | bar: 2022-02-14 18 F to 2022-03-21 25 F
Implement sFTP to S3 calling Lambda Step Functions calling SSIS (which calls PostgreSQL SP) | 2022-02-18 | 2022-03-25 | Software Team |  |  | 10 hrs | bar: 2022-02-14 18 F to 2022-03-21 25 F
Implement API consuming import data | 2022-02-18 |  | Software Team |  |  | TBC hours
Matific Phase
API specification | 2022-02-04 | 2022-02-18 | Willem Boshoff |  |  | ? | bar: 2022-01-31 4 F to 2022-02-14 18 F
Rewrite SSIS script for use with PostgreSQL : Export_Matific_Registration.dtsx | 2022-02-18 | 2022-03-18 | Software Team |  |  | 20 hrs | bar: 2022-02-14 18 F to 2022-03-14 18 F
Testing complete import process | 2022-02-18 | 2022-03-18 | Software Team |  |  | 20 hrs | bar: 2022-02-14 18 F to 2022-03-14 18 F
API need to be spec'd (at the least are we producing or consuming API etc) | 2022-02-18 |  | Software Team |  |  | TBC
School Imports Phase
Testing complete import process | 2022-03-04 | 2022-03-18 | Software Team |  |  | 20 hrs | bar: 2022-02-28 4 F to 2022-03-14 18 F
Possible additional modernisations
SSO for facilitators :: no longer manually importing users via "Click Email Tracker.xlsx" and importing users to Click table but passwords and Auth is done against Google AD; this assumes that ALL data in the Excel is in Google AD and nothing is being manually added to the file after it is exported | 2022-02-04 | 2022-02-25 | Software Team |  |  | 40 hrs (outside SoW but can be included at no extra cost) | bar: 2022-01-31 4 F to 2022-02-21 25 F
Re-develop both web portals and move to S3 or Amplify with API Gateway and Lambda (purely serverless stack) |  |  | Software Team |  |  | (outside SoW)
Adding import wizards to the Admin portal to show data before accepting import |  |  | Software Team |  |  | (outside SoW)
Additional reports burst/sent on regular dates |  |  | Software Team |  |  | (outside SoW)
AWS as a Platform Testing Phase
Account 2 - AWS Staging Environment with React.js Web Applications, Glue, QuickSight and Single-AZ Aurora MySQL Databases | 2021-12-15 | 2021-12-21 |  |  |  | Start once Modernization Scope of Work has been finalized Estimated time frame to configure of 1 to 2 weeks | bar: 2021-12-13 15 W to 2021-12-20 21 T
Setup base account configuration as per AWS Best Practices including secure IAM setup and virtual MFA, disable Regions not in use, account information setup etc. |  |  | Silicon Team
Setup cost Alerts and weekly Reports based on the Proposal monthly AWS cost estimates in CloudHealth or AWS Budgets. Setup 50% and 100% Actual and 50%, 100%, 150% Forecasted alerts and include project teams. Alerts and reports to be sent to: awsbudgetalerts@overdrive.co.za Customer to setup awsbudgetalerts@ mail address and forward to team monitoring the AWs budgets and costs. The customer must monitor these budget and cost alerts. |  |  | Silicon Team
When adding a new AWS service - must look at the additional billing incurred on day 1 and day 3 and report any unexpected billing on day 3. (All days are business days) The reason for this is to ensure that the customer does not incur unforeseen costs. The Budget Alerts are configured to alert if the spend will or has exceeded the budget set. Note to customer - please ensure that measures are in place to monitor your billing. Please notify us immediately if any unforeseen costs are incurred. |  |  | Silicon Team
On authorization setup Trend Cloud Conformity on an annual subscription, billed monthly |  |  | Silicon Team
Configure AWS Services as per authorised Architecture
AWS Identity and Access Management (IAM) |  |  | Silicon Team
AWS CloudTrail |  |  | Silicon Team
AWS Trusted Advisor |  |  | Silicon Team
AWS Config |  |  | Silicon Team
Amazon Virtual Private Cloud (VPC) in Cape Town |  |  | Silicon Team
2 Availability Zones |  |  | Silicon Team
Internet Gateway |  |  | Silicon Team
Amazon API Gateway |  |  | Silicon Team
SSL certificate (Certificate Manager) |  |  | Silicon Team
Elastic Load Balancer |  |  | Silicon Team
Amazon Simple Notification Service (SNS) |  |  | Silicon Team
Amazon Elastic Compute Cloud (EC2) |  |  | Silicon Team
Private Subnet - A1 |  |  | Silicon Team
Windows EC2 running front end .NET |  |  | Silicon Team
Private Subnet - B1 |  |  | Silicon Team
Private Subnet - A2 |  |  | Silicon Team
ClickDW Primary |  |  | Silicon Team
Amazon Aurora MySQL Primary |  |  | Silicon Team
ClickMart Primary |  |  | Silicon Team
Amazon Aurora MySQL Primary |  |  | Silicon Team
ClickStaging Primary |  |  | Silicon Team
Amazon Aurora MySQL Primary |  |  | Silicon Team
AWS Amplify |  |  | Silicon Team
Amplify Admin Site |  |  | Silicon Team
Amplify Learner Site |  |  | Silicon Team
AWS Lambda |  |  | Silicon Team
Terraform |  |  | Silicon Team
AWS Backup |  |  | Silicon Team
Amazon CloudWatch |  |  | Silicon Team
AWS Systems Manager |  |  | Silicon Team
Amazon Simple Storage Service (S3) |  |  | Silicon Team
AWS Key Management Service (KMS) |  |  | Customer Team
AWS Secrets Manager |  |  | Customer Team
AWS CodeDeploy |  |  | Customer Team
AWS CodeCommit |  |  | Customer Team
Deploy Trend Workload Security to protect all EC2 instances and workloads. |  |  | Silicon Team
Conduct a security and AWS best practice validation using Cloud Conformity with reporting, and or a manual design and architecture validation assessment report. Implement any outstanding requirements. Re-run the validation reporting process. |  |  | Silicon Team
Schedule a handover meeting with project teams |  |  | Silicon Team
Integrate the migrated workloads (application servers, databases, data, or infrastructure services) with the AWS environment and services |  |  | Customer Team
Customer application testing phase |  |  | Customer Team
Customer application load testing phase. Customer procured load testing tools may include K6/Load Impact, Gremlin etc. |  |  | Customer Team |  |  | Optional
Migration Phase
Account 1 - AWS Production Environment with React.js Web Applications, Glue, QuickSight and Multi-AZ Aurora MySQL Databases | [5 empty] | Start once Staging Environment has been full tested and the need for Production switchover is necessary Estimated time frame to configure of 3 to 4 weeks
Setup base account configuration as per AWS Best Practices including secure IAM setup and virtual MFA, disable Regions not in use, account information setup etc. |  |  | Silicon Team
Setup cost Alerts and weekly Reports based on the Proposal monthly AWS cost estimates in CloudHealth or AWS Budgets. Setup 50% and 100% Actual and 50%, 100%, 150% Forecasted alerts and include project teams. Alerts and reports to be sent to: awsbudgetalerts@overdrive.co.za Customer to setup awsbudgetalerts@ mail address and forward to team monitoring the AWs budgets and costs. The customer must monitor these budget and cost alerts. |  |  | Silicon Team
When adding a new AWS service - must look at the additional billing incurred on day 1 and day 3 and report any unexpected billing on day 3. (All days are business days) The reason for this is to ensure that the customer does not incur unforeseen costs. The Budget Alerts are configured to alert if the spend will or has exceeded the budget set. Note to customer - please ensure that measures are in place to monitor your billing. Please notify us immediately if any unforeseen costs are incurred. |  |  | Silicon Team
On authorization setup Trend Cloud Conformity on an annual subscription, billed monthly |  |  | Silicon Team
Configure AWS Services as per authorised Architecture
AWS Identity and Access Management (IAM) |  |  | Silicon Team
AWS CloudTrail |  |  | Silicon Team
AWS Trusted Advisor |  |  | Silicon Team
AWS Config |  |  | Silicon Team
Amazon Virtual Private Cloud (VPC) in Cape Town |  |  | Silicon Team
2 Availability Zones |  |  | Silicon Team
Internet Gateway |  |  | Silicon Team
Amazon API Gateway |  |  | Silicon Team
SSL certificate (Certificate Manager) |  |  | Silicon Team
Elastic Load Balancer |  |  | Silicon Team
Amazon Simple Notification Service (SNS) |  |  | Silicon Team
Amazon Elastic Compute Cloud (EC2) |  |  | Silicon Team
Private Subnet - A1 |  |  | Silicon Team
Windows EC2 running front end .NET |  |  | Silicon Team
Private Subnet - B1 |  |  | Silicon Team
Private Subnet - A2 + B2 |  |  | Silicon Team
ClickDW Primary |  |  | Silicon Team
ClickDW Read Replica |  |  | Silicon Team
Amazon Aurora MySQL Primary |  |  | Silicon Team
Amazon Aurora MySQL Read Replica |  |  | Silicon Team
ClickMart Primary |  |  | Silicon Team
ClickMart Read Replica |  |  | Silicon Team
Amazon Aurora MySQL Primary |  |  | Silicon Team
Amazon Aurora MySQL Read Replica |  |  | Silicon Team
ClickStaging Primary |  |  | Silicon Team
ClickStaging Read Replica |  |  | Silicon Team
Amazon Aurora MySQL Primary |  |  | Silicon Team
Amazon Aurora MySQL Read Replica |  |  | Silicon Team
AWS Amplify |  |  | Silicon Team
Amplify Admin Site |  |  | Silicon Team
Amplify Learner Site |  |  | Silicon Team
AWS Lambda |  |  | Silicon Team
Terraform |  |  | Silicon Team
AWS Backup |  |  | Silicon Team
Amazon CloudWatch |  |  | Silicon Team
AWS Systems Manager |  |  | Silicon Team
Amazon Simple Storage Service (S3) |  |  | Silicon Team
AWS Key Management Service (KMS) |  |  | Customer Team
AWS Secrets Manager |  |  | Customer Team
AWS CodeDeploy |  |  | Customer Team
AWS CodeCommit |  |  | Customer Team
Deploy Trend Workload Security to protect all EC2 instances and workloads. |  |  | Silicon Team
Conduct a security and AWS best practice validation using Cloud Conformity with reporting, and or a manual design and architecture validation assessment report. Implement any outstanding requirements. Re-run the validation reporting process. |  |  | Silicon Team
Schedule a handover meeting with project teams |  |  | Silicon Team
Integrate the migrated workloads (application servers, databases, data, or infrastructure services) with the AWS environment and services |  |  | Customer Team
Customer application testing phase |  |  | Customer Team
Customer application load testing phase. Customer procured load testing tools may include K6/Load Impact, Gremlin etc. |  |  | Customer Team
Perform cutover to the migrated services with a customer designed rollback plan |  |  | Customer Team
Customer satisfaction checkpoint - send CSAT Deliverables: Migrated applications and workloads validated and running in the production environment in AWS |  |  | Silicon Team
Account 3
Setup base account configuration as per AWS Best Practices including secure IAM setup and virtual MFA, disable Regions not in use, account information setup etc. |  |  | Silicon Team
Setup cost Alerts and weekly Reports based on the Proposal monthly AWS cost estimates in CloudHealth or AWS Budgets. Setup 50% and 100% Actual and 50%, 100%, 150% Forecasted alerts and include project teams. Alerts and reports to be sent to: awsbudgetalerts@overdrive.co.za Customer to setup awsbudgetalerts@ mail address and forward to team monitoring the AWs budgets and costs. The customer must monitor these budget and cost alerts. |  |  | Silicon Team
On authorization setup Trend Cloud Conformity on an annual subscription, billed monthly |  |  | Silicon Team
Configure AWS Services as per authorised Architecture
Configure Optional AWS Services as per authorised Architecture
Deploy Trend Workload Security to protect all EC2 instances and workloads. |  |  | Silicon Team
Conduct a security and AWS best practice validation using Cloud Conformity with reporting, and or a manual design and architecture validation assessment report. Implement any outstanding requirements. Re-run the validation reporting process. |  |  | Silicon Team
Schedule a handover meeting with project teams |  |  | Silicon Team
Integrate the migrated workloads (application servers, databases, data, or infrastructure services) with the AWS environment and services |  |  | Customer Team
Customer application testing phase |  |  | Customer Team
Customer application load testing phase. Customer procured load testing tools may include K6/Load Impact, Gremlin etc. |  |  | Customer Team
Best Practice Pre-Go Live Recommendations It is Best Practice to:
Setup Trend Cloud Conformity for security and governance alerts and reporting. Run a security and compliance assessment report. Remediate and implement any improvements. Re-run a security and compliance assessment report for improvement validation. |  |  | Silicon Team
Ensure that Trend workload security is deployed to protect all EC2 instances and workloads.
If Cloud Conformity not authorized conduct an AWS Security and Best Practice validation assessment for each account. Remediate and implement limited improvements. Re-conduct the AWS Security and Best Practice validation assessment for each account. |  |  | Silicon Team
Implement Amazon CloudWatch Dashboard for monitoring. Implement alerting for project teams |  |  | Silicon Team
Setup AWS Backup Using AWS Backup, you can centrally configure backup policies and monitor backup activity for AWS resources, such as Amazon EBS volumes, Amazon RDS databases, Amazon DynamoDB tables, Amazon EFS file systems, AWS Storage Gateway volumes. |  |  | Silicon Team
Enable Versioning on all important and Production Amazon S3 Buckets |  |  | Silicon Team
Generate a provisional DR, Backup and Restore Policy |  |  | Silicon Team
Check and redeem all remaining AWS credits |  |  | Silicon Team
Preliminary Optimization Phase
Conduct an initial, basic Cost Optimization assessment and present any recommendations for later implementation (e.g. obvious rightsizing opportunities, using Reserved Instances or AWS Savings Plans). Generally workloads need to run for one to three months in production before a baseline can be understood for cost optimization. |  |  | Silicon Team
Present the assessment findings via email or on a call |  |  | Silicon Team
Update AWS Budgets and AWS Budget Reports |  |  | Silicon Team
If not already implemented and if applicable: Implement AWS Systems Manager Agent (SSM Agent) to automate EC2 Patch Management to reduce the Maintenance Agreement. Implement Amazon Inspector Agent. |  |  | Silicon Team
Project Closure Phase
Provide limited training about the AWS environment running migrated or deployed applications to the customer |  |  | Silicon Team
Handover the final architecture diagrams, implementation notes, and DR Backup and Restore Policy |  |  | Silicon Team
Email the AWS POA Customer Sign‐Off Template |  |  | Silicon Team
Sign the AWS POA Customer Sign‐Off Template with Project Deliverables |  |  | Customer Team
Complete the AWS Customer Satisfaction Survey (CSAT) and notify the Silicon projects team once completed |  |  | Customer Team
Optional Trend Cloud Conformity
Link your AWS account |  |  | Silicon Team
Setup automated Cloud Conformity security and governance reporting and alerting |  |  | Silicon Team
Setup access to Cloud Conformity Console |  |  | Silicon Team
Basic Cloud Conformity training |  |  | Silicon Team
Optional Post-Migration Optimization Phase
Conduct a full Cost Optimization assessment and present any recommendations for implementation (e.g. rightsizing EC2, using Reserved Instances or AWS Savings Plans) |  |  | Silicon Team
Present the assessment findings on a call |  |  | Silicon Team
Update AWS Budgets and AWS Budget Reports |  |  | Silicon Team
If not already implemented and if applicable: Implement AWS Systems Manager Agent (SSM Agent) to automate EC2 Patch Management to reduce the Maintenance Agreement. Implement Amazon Inspector Agent. |  |  | Silicon Team
Run a Trend Cloud Conformity security and compliance assessment report. Remediate and implement any improvements. Re-run a security and compliance assessment report for improvement validation. |  |  | Silicon Team
Customer satisfaction checkpoint - send CSAT |  |  | Silicon Team
Optional Support and Maintenance (Operations) Phase
Provide ongoing AWS support and AWS and security maintenance under agreement to meet requirements, including operations, security and cost optimization tasks. |  |  | Silicon Team
Access to support and our AWS team would be on an Agreement basis for several business, continuity and service delivery reasons.
AWS, server and security maintenance |  |  | Silicon Team
Trend Cloud Conformity automated security and governance reporting and alerting |  |  | Silicon Team
Monitoring and alerting |  |  | Silicon Team
Review logs |  |  | Silicon Team
Backup monitoring |  |  | Silicon Team
System and Security patch management |  |  | Silicon Team
Support, troubleshooting and escalation procedures |  |  | Customer and Silicon Team
Change management |  |  | Customer Team
Cost optimization reviews |  |  | Customer and Silicon Team
Operational optimization reviews |  |  | Customer and Silicon Team
Conduct annual AWS and security best practice validation assessments |  |  | Silicon Team
Conduct annual AWS Cost Optimization assessments |  |  | Silicon Team
Optional AWS Well-Architected Review Phase AWS Well-Architected Review per workload - evaluate the current architectures and implement operational excellence, security, reliability, performance efficiency, and cost optimization improvements. In this process AWS will provide you with $5000 in service credits if you leverage an approved AWS Well-Architected Partner, like us, to help improve the workload.
Run a Trend Cloud Conformity security and compliance assessment report in preparation for, and before we conduct the AWS Well-Architected Review. |  |  | Silicon Team
If Trend Cloud Conformity not authorized conduct an AWS Security and Best Practice assessment in preparation for, and before we conduct the AWS Well-Architected Review |  |  | Silicon Team
Conduct the AWS Well-Architected Review. |  |  | Silicon Team
Generate a provisional Project Plan with high risk remediations to be implemented |  |  | Silicon Team
Select and assign task owners for remediations. |  |  | Customer Team
Submit a proposal based on the customer selected remediations and tasks assigned to the Silicon Team for remediation or implementation |  |  | Customer Team
Authorise the Proposal to be submitted |  |  | Customer Team
Implement any priority Assessment and AWS Well-Architected Review and Recommendations and Improvements. Paid Improvements must start no later than 30 days after the review. |  |  | Customer and Silicon Team
Submit the AWS Well-Architected Review remediations milestone update to AWS. AWS requires a minimum of 25% of the HRI (high risk items) to be remediated by us before we submit this milestone update to apply for the credits |  |  | Silicon Team
Complete the AWS Customer Satisfaction Survey (CSAT) once emailed by AWS, and notify the Silicon projects team once completed |  |  | Customer Team
Apply the $5000 credits to one of your AWS accounts once AWS emails you the promo credit code. |  |  | Customer Team
Formulas:
Week 2 = [Week 1]+7
Week 3 = [Week 2]+7
Week 4 = [Week 3]+7
Week 5 = [Week 4]+7
Week 6 = [Week 5]+7
Week 7 = [Week 6]+7
Week 8 = [Week 7]+7
Week 9 = [Week 8]+7
Week 10 = [Week 9]+7
Week 11 = [Week 10]+7
Week 12 = [Week 11]+7
Week 13 = [Week 12]+7
Week 14 = [Week 13]+7
Week 15 = [Week 14]+7
Week 16 = [Week 15]+7
Week 17 = [Week 16]+7
Week 18 = [Week 17]+7
Week 19 = [Week 18]+7
Week 20 = [Week 19]+7
Week 21 = [Week 20]+7
Week 22 = [Week 21]+7
Week 23 = [Week 22]+7
Week 24 = [Week 23]+7
Week 25 = [Week 24]+7
Week 26 = [Week 25]+7
Week 27 = [Week 26]+7
Week 28 = [Week 27]+7
Week 29 = [Week 28]+7
Week 30 = [Week 29]+7
Week 31 = [Week 30]+7
Week 32 = [Week 31]+7
Week 33 = [Week 32]+7
Week 34 = [Week 33]+7
Week 35 = [Week 34]+7
Week 36 = [Week 35]+7
Week 37 = [Week 36]+7
Week 38 = [Week 37]+7
Week 39 = [Week 38]+7
Week 40 = [Week 39]+7
Week 41 = [Week 40]+7
Week 42 = [Week 41]+7
Week 43 = [Week 42]+7
Week 44 = [Week 43]+7
Week 45 = [Week 44]+7
Week 46 = [Week 45]+7
Week 47 = [Week 46]+7
Week 48 = [Week 47]+7
Week 49 = [Week 48]+7
Week 50 = [Week 49]+7
Week 51 = [Week 50]+7
Week 52 = [Week 51]+7
Week 53 = [Week 52]+7
Week 54 = [Week 53]+7
Note on E14: Use ONLY the drop-down menu to select the task owner name. Entering text that is not from the menu will result in reporting errors in Tab 4.

## Click Processes
|  |  | 531 | 121 |  |  | 82
Import processes | Process | File / Script | Mod Hours | # SP | Will Replicate | Have Replicated | Rep SP | Bus Rules Doc | Tested SP | Source | Is Automated | Can Automate | Will Modernise (add to SoW) | If so, what tech | Used in
DDD | pNewDataImportID |  |  |  | Y | Y |  | Y
| pUpdateDataImport |  |  |  | Y | Y |  | Y
|  | Fetch_Learner_DDD.dtsx |  | 0 | Y | Y | 0 | Y |  | SSIS |  |  |  |  | DDD Import
|  | Import_Learner_DDD.dtsx |  | 4 | Y | Y | 4 | Y |  | SSIS |  |  |  |  | DDD Import
|  | CompleteDDDFileImport.SQL |  | 3 | Y | Y | 3 | Y |  | SSIS
| internal.pUpdateDDDIDs | Import_learner_DDD_Finalize.dtsx |  | 7 | Y | Y | 7 | Y |  | SSIS |  |  |  |  | DDD Import
| internal.pUpdateSourceLearner |  |  |  | Y | Y | 0 | Y
| internal.pUpdateLearnerFromSourceLearnerFirstUsableData |  |  |  | Y | Y | 0 | Y
| internal.pUpdateSchoolDataSource |  |  |  | Y | Y | 0 | Y
|  | LearnerRegistrationCheck.SQL | 60 | 9 | Y | Y | 9 | Y |  | SSIS |  |  | Automate current manual process, if possible due to data consistency [Gavin to advise]
|  | TransferDW_Learner_Registrations.dtsx | 60 | 8 | Y | Y | 8 | Y |  | SSIS |  |  | Automate current manual process, if possible due to data consistency [Gavin to advise]
|  |  | 60 | [9 empty] | Testing and rewriting 6 slow running queries
|  |  | 80 | [9 empty] | Testing entire data import processes for DDD + CEMIS
|  |  | 40 | [9 empty] | Documenting above item (data import processes) as runbooks
|  |  | 32 | [9 empty] | Implement sFTP to S3 calling Lambda Step Functions calling SSIS (which calls PostgreSQL SP) (around 6 processes)
CEMIS | pNewDataImportID | Import_learner_cemis_simple.dtsx |  | 7 | Y | Y | 7 | Y |  | SSIS |  |  |  |  | CEMIS Import
| reporting.pValidateCEMISLearner |  |  |  | Y | Y | 0 | Y
| dbo.pUpdateLearnerCEMIS |  |  |  | Y | Y | 0 | Y
| internal.pUpdateSourceLearner |  |  |  | Y | Y | 0 | Y
| ClickDW.internal.pUpdateLearnerFromSourceLearnerFirstUsableData |  |  |  | Y | Y | 0 | Y
| internal.pUpdateSchoolDataSource |  |  |  | Y | Y | 0 | Y
|  | LearnerRegistrationCheck.SQL |  | 9 | Y | Y | 9 | Y |  | SSIS
| pLearnersRegisterFromSourceLearner | TransferDW_Learner_Registrations.dtsx |  | 8 | Y | Y | 8 | Y |  | SSIS |  |  |  |  | DDD & CEMIS Import
| internal.pNewDataImportID |  |  |  | Y | Y | 0 | Y
| internal.pTransferLearner |  |  |  | Y | Y | 0 | Y
| internal.pUpdateLearnerFromSourceLearner |  |  |  | Y | Y | 0 | Y
| internal.pUpdateDataImport |  |  |  | Y | Y | 0 | Y
| internal.pGenerateUserNames |  |  |  | Y | Y | 0 | Y
| internal.pGetProgrammeRegistrationRegionList |  |  |  | Y | Y | 0 | Y
| internal.pExtractReflectiveLearningRegistrationLearnerList |  |  |  | Y | Y | 0 | Y
|  | Reports_Generate.dtsx |  | 2 | Y | Y | 2
| clickdw.reporting.pgeneratereports |  |  |  | Y | Y | 0
| clickdw.dbo.fgetrelatedhierarchyrootentityid |  |  |  | Y | Y | 0
| internal.pNewDataImportID | TransferDW_Learner.dtsx |  | 3 | Y | Y | 3 | Y |  | SSIS
| internal.pTransferLearner |  |  |  | Y | Y | 0 | Y
| internal.pUpdateDataImport |  |  |  | Y | Y | 0 | Y
|  | Import_Learner_CEMIS.dtsx |  | 7 | Y | Y | 7 |  |  | SSIS
| pNewDataImportID |  |  |  | Y | Y | 0 | Y
| reporting.pValidateCEMISLearner |  |  |  | Y | Y | 0 | Y
| dbo.pUpdateLearnerCEMIS |  |  |  | Y | Y | 0 | Y
| pUpdateDataImport |  |  |  | Y | Y | 0 | Y
| internal.pUpdateSourceLearner |  |  |  | Y | Y | 0 | Y
| ClickDW.internal.pUpdateLearnerFromSourceLearnerFirstUsableData |  |  |  | Y | Y | 0 | Y
| dbo.pnewdataimportid |  |  |  | Y | Y
| dbo.pupdatedataimport |  |  |  | Y | Y
Reading Eggs | internal.pUpdateSchoolDataSource | Export_ReadingEggs.dtsx | 30 | 2 | Y | B | 0 |  |  | SSIS |  |  | Rewrite SSIS script for use with PostgreSQL
|  |  | 30 | [9 empty] | Testing complete import process
|  |  | 10 | [9 empty] | Implement sFTP to S3 calling Lambda Step Functions calling SSIS (which calls PostgreSQL SP)
|  |  | ? | [9 empty] | Implement API consuming import data
| File extraction done daily; basic data points |  |  |  | Y | Y | 0
| Data points sent daily |  |  |  | Y | Y | 0
| Ad hoc extraction; custom data points |  |  |  | Y | Y | 0 |  |  | Manual | No
| Usage on program extracted on Sundays | TransferDW_ReadingEggs_LearnerList.dtsx |  | 3 | Y | P | 0 |  |  | SSIS
| internal.pNewDataImportID |  |  |  | Y | Y | 0 | Y
| internal.pTransferReadingEggsLearnerList |  |  |  | Y | Y | 0
| internal.pUpdateDataImport |  |  |  | Y | Y | 0
| internal.pExtractReadingEggsLearner | TransferDW_ReadingEggs.dtsx |  | 6 | Y | P | 0 |  |  | SSIS
| internal.pNewDataImportID |  |  |  | Y | Y | 0 | Y
| internal.pUpdateLearnerFromReadingEggs |  |  |  | Y | Y | 0
| internal.pTransferReadingEggs2 |  |  |  | Y | Y | 0
| internal.pUpdatePersonProgrammeActivity |  |  |  | Y | Y | 0
| internal.pActivateSchoolReadingEggs |  |  |  | Y | Y | 0
| internal.pUpdateDataImport |  |  |  | Y | Y | 0
| internal.pExtractReadingEggsEducator | Import_ReadingEggs_LearnerList.dtsx |  | 2 | Y | P | 0 |  |  | SSIS
| pNewDataImportID |  |  |  | Y | Y | 0 | Y
| pUpdateDataImport |  |  |  | Y | Y | 0
|  | Fetch_ReadingEggs.dtsx |  |  | Y |  | 0 |  |  | SSIS
| pNewDataImportID | Import_ReadingEggs_DistrictLearnerList.dtsx |  | 2 | Y | Y | 2 | Y |  | SSIS
| pUpdateDataImport | clickstaging.dbo.pupdatedataimport |  |  | Y | Y | 0
| pNewDataImportID | Import_ReadingEggs.dtsx |  | 2 | Y | Y | 2 | Y |  | SSIS
| pUpdateDataImport |  |  |  | Y | Y | 0
| Get Fetch Info | FetchImport_AWS-CSV.dtsx |  |  | Y | Y
| Get credentials login S3 bucket-SQL query |  |  |  | Y | Y
| Get DataImportID | clickstaging.dbo.pnewdataimportid |  |  | Y | Y
| Get Imports to transfer SQL query | TransferDW_StoredProc.dstx |  |  | Y | Y
| Get STAGING Data Import Values- SQL query | pNewDataImportID |  |  |  | Y
| clickdw.internal.ptransferparentconsenthomelearning |  |  |  | Y | B
| clickdw.internal.pdataimportlogtext |  |  |  | Y | Y
| credetials login S3 bucket - SQL query |  |  |  | Y | Y
Matific (uses same login as RE) | [6 empty] | 0
| Send unique identifier details back | Export_Matific_Registration.dtsx | 20 | 2 | Y |  | 0 |  |  | SSIS |  |  | Rewrite SSIS script for use with PostgreSQL
|  |  | 20 | [9 empty] | Testing complete import process
| Learners are going to be registered through API | Reports_Generate.dtsx | ? |  | Y |  | 0 | [5 empty] | API need to be spec'd (at the least are we producing or consuming API etc)
| internal.pExtractMatificRegistrationSchoolList |  |  |  | Y |  | 0
| internal.pExtractMatificRegistrationLearnerList |  |  |  | Y |  | 0
| relatively new program, updates still being done manually |  |  |  | Y |  | 0
Mathseeds | pNewDataImportID | Import_Mathseeds.dtsx |  | 2 | N | Y | 2 | Y |  | SSIS
| pUpdateDataImport |  |  |  | N | Y | 0
| internal.pNewDataImportID | TransferDW_Mathseeds.dtsx |  | 4 | N | Y | 4 | Y |  | SSIS
| internal.pTransferMathseeds |  |  |  | N |  | 0
| internal.pUpdatePersonProgrammeActivity |  |  |  | N |  | 0
| internal.pUpdateDataImport |  |  |  | N | Y | 0
School Import | pNewDataImportID | Import_Parent.dtsx |  | 2 | Y | Y | 2 | Y |  | SSIS
|  |  | 20 | [9 empty] | Testing complete import process
| pUpdateDataImport |  |  |  | Y | Y | 0
| internal.pNewDataImportID | TransferDW_Parent.dtsx |  | 3 | Y | Y | 3 | Y |  | SSIS
| internal.pTransferParent |  |  |  | Y |  | 0
| internal.pUpdateDataImport |  |  |  | Y | Y | 0
| internal.pTransfer |  |  |  | Y
| Master list imported for all regions except FS and WC | Import_MasterList.dtsx |  | 2 | Y | B | 0 |  |  | SSIS
Quizzes :: Mobenzi closed so no longer required |  | FetchImport_QuizResults_Mobenzi.dtsx |  | 2 | N |  | 0 |  |  | SSIS
| pNewDataImportID |  |  |  | N |  | 0 | Y
| pUpdateDataImpor | FetchImport_Mobenzi.dtsx |  | 2 | N |  | 0 |  |  | SSIS
| pNewDataImportID | TransferDW_Quiz.dtsx |  | 3 | N |  | 0 | Y |  | SSIS
| internal.pNewDataImportID |  |  |  | N |  | 0 | Y
| internal.pTransferQuiz |  |  |  | N |  | 0
| internal.pUpdateDataImport |  |  |  | N |  | 0
System daily maintainance (Gavin to confirm if it's being used) | pUpdateDataImport | System_Daily_Maintenance.dtsx |  | 3 | N |  | 0 |  |  | SSIS
| ClickCOMMON..sp_updatestats | [5 empty] | 0
| ClickDW..sp_updatestats | [5 empty] | 0
| ClickSTAGING..sp_updatestats | [5 empty] | 0
Reports generator ((Gavin to confirm if it's being used) | reporting.pGenerateReports | Reports_Generate.dtsx |  | 1 | N |  | 0 |  |  | SSIS
Registration data | pNewDataImportID | Import_Learner_Registrations.dtsx |  | 2 | N |  | 0 | Y |  | SSIS | Yes
| pUpdateDataImport | [5 empty] | 0
Lift and shift | Weekly automated | [11 empty] | Yes
Rebuild into streamlined interface | Modernise service
Data set library | Business process
Learner's grades detection | create data set library to predefine data filed extractions which will be pre-approved | [9 empty] | Yes
Specific Learner details | source system | [9 empty] | No
Streamline registration | added manually | [11 empty] | Yes | TBD
projected goal is to have single sign on for all programs
Data capturing | streamlining registration process part of migration upgrades | [11 empty] | Yes, needing more structure
Deleted learners | Data export specifically built for The Click Foundation
6 monthly cleanup
Unknown |  | FetchImport_AWS-S3-CSV.dtsx |  | 2 | N |  | 0 |  |  | SSIS
0
| pNewDataImportID | [5 empty] | 0 | Y
| pUpdateDataImpor | Import_CSV.dtsx |  | 3 | N |  | 0 |  |  | SSIS
| pNewDataImportID | [5 empty] | 0 | Y
| pValidateParent2 | [5 empty] | 0
| pUpdateDataImport | Import_Environment.dtsx |  | 2 | N |  | 0 |  |  | SSIS
| pNewDataImportID | [5 empty] | 0 | Y
| pUpdateDataImport | TransferDW_StoredProc.dtsx |  | 2 | N |  | 0 |  |  | SSIS
| internal.pNewDataImportID |  |  |  |  | Y | 0 | Y
| internal.pUpdateDataImport |  |  |  |  | Y | 0
0
| internal.pdataimportloginsert |  |  |  |  | Y | 0
| dbo.fgetsystemparameter | [5 empty] | 0
| dbo.pnewdataimportid |  |  |  |  | Y | 0 | Y
| dbo.pupdatedataimport |  |  |  |  | Y | 0
| internal.pdataimportloginsertcount |  |  |  |  | Y | 0
| internal.ptemporalstatus |  |  |  |  | Y | 0
| dbo.plearnersregisterfromsourcelearner |  |  |  |  | Y | 0
0
|  |  | 69 | [9 empty] | Project management

## Stored procedures
SSIS Process | Stored Procedure Name | Nested Stored Procedures | File Script / File Name | Associated Process | Min Time Estimate | Max Time Estimate
DDD
| function dbo.pnewdataimportid |  |  | Import_Learner_DDD.dtsx
| function dbo.pupdatedataimport |  |  | Import_Learner_DDD.dtsx
| function internal.pupdatedddids | procedure internal.pdataimportloginsert |  | Import_learner_DDD_Finalize.dtsx
|  | function internal.pupdatedataimport |  | Import_learner_DDD_Finalize.dtsx
|  | function internal.pnewdataimportid |  | Import_learner_DDD_Finalize.dtsx
| procedure internal.pupdatesourcelearner |  |  | Import_learner_DDD_Finalize.dtsx
| procedure internal.pupdatelearnerfromsourcelearnerfirstusabledata |  |  | Import_learner_DDD_Finalize.dtsx
|  | procedure internal.pupdatesourcelearner |  | Import_learner_DDD_Finalize.dtsx
|  | procedure internal.pupdatesourcelearner |  | Import_learner_DDD_Finalize.dtsx
|  | procedure internal.pdataimportloginsertcount |  | Import_learner_DDD_Finalize.dtsx
|  | procedure internal.ptemporalstatus |  | Import_learner_DDD_Finalize.dtsx
|  | procedure internal.pdataimportloginsert |  | Import_learner_DDD_Finalize.dtsx
| function dbo.plearnersregisterfromsourcelearner | function dbo.pnewdataimportid |  | TransferDW_Learner_Registrations.dtsx
|  | function dbo.pupdatedataimport |  | TransferDW_Learner_Registrations.dtsx
| function internal.pnewdataimportid |  |  | TransferDW_Learner_Registrations.dtsx
| procedure internal.ptransferlearner |  |  | TransferDW_Learner_Registrations.dtsx
| procedure internal.pupdatelearnerfromsourcelearner |  |  | TransferDW_Learner_Registrations.dtsx
| function internal.pUpdateDataImport |  |  | TransferDW_Learner_Registrations.dtsx
| procedure internal.pgenerateusernames | procedure internal.pgenerateusernamesmatific |  | TransferDW_Learner_Registrations.dtsx
|  | procedure internal.pgenerateusernamesreflectivelearning |  | TransferDW_Learner_Registrations.dtsx
CEMIS
| function dbo.pnewdataimportid |  |  | Import_learner_cemis_simple.dtsx
| function reporting.pvalidatecemislearner |  |  | Import_learner_cemis_simple.dtsx
| procedure dbo.pupdatelearnercemis |  |  | Import_learner_cemis_simple.dtsx
| function dbo.pupdatedataimport |  |  | Import_learner_cemis_simple.dtsx
| procedure internal.pupdatesourcelearner |  |  | Import_learner_cemis_simple.dtsx
| procedure internal.pupdatelearnerfromsourcelearnerfirstusabledata |  |  | Import_learner_cemis_simple.dtsx
| procedure internal.pupdateschooldatasource |  |  | Import_learner_cemis_simple.dtsx
| procedure reporting.pgeneratereports |  |  | Reports_Generate.dtsx
| function dbo.plearnersregisterfromsourcelearner | function dbo.pnewdataimportid |  | TransferDW_Learner_Registrations.dtsx
|  | function dbo.pupdatedataimport |  | TransferDW_Learner_Registrations.dtsx
| function internal.pnewdataimportid |  |  | TransferDW_Learner_Registrations.dtsx
| procedure internal.ptransferlearner |  |  | TransferDW_Learner_Registrations.dtsx
| procedure internal.pupdatelearnerfromsourcelearner |  |  | TransferDW_Learner_Registrations.dtsx
| function internal.pUpdateDataImport |  |  | TransferDW_Learner_Registrations.dtsx
| procedure internal.pgenerateusernames | procedure internal.pgenerateusernamesmatific |  | TransferDW_Learner_Registrations.dtsx
|  | procedure internal.pgenerateusernamesreflectivelearning |  | TransferDW_Learner_Registrations.dtsx

## SoW
Once-off Cost
Import Process | Description | Hours | Rate | Total
DDD+CEMIS | Automate current manual process : LearnerRegistrationCheck.SQL, if possible due to data consistency [Gavin to advise] | 60 | 790 | 47400
| Automate current manual process : TransferDW_Learner_Registrations.dtsx, if possible due to data consistency [Gavin to advise] | 60 | 790 | 47400
| Testing and rewriting 6 slow running queries | 60 | 790 | 47400
| Testing entire data import processes for DDD + CEMIS | 80 | 790 | 63200
| Documenting above item (data import processes) as runbooks | 40 | 790 | 31600
| Implement sFTP to S3 calling Lambda Step Functions calling SSIS (which calls PostgreSQL SP) (around 6 processes) | 32 | 790 | 25280
Reading Eggs | Rewrite SSIS script for use with PostgreSQL : Export_ReadingEggs.dtsx | 30 | 790 | 23700
| Testing complete import process | 30 | 790 | 23700
| Implement sFTP to S3 calling Lambda Step Functions calling SSIS (which calls PostgreSQL SP) | 10 | 790 | 7900
| Implement API consuming import data | TBC | 790 | TBC
Matific | Rewrite SSIS script for use with PostgreSQL : Export_Matific_Registration.dtsx | 20 | 790 | 15800
| Testing complete import process | 20 | 790 | 15800
| API need to be spec'd (at the least are we producing or consuming API etc) | TBC | 790 | TBC
School Imports | Testing complete import process | 20 | 790 | 15800
| Project Management | 69 | 900 | 62100
| Total Cost excl VAT |  |  | 427080
Monthly Cost
| Description | Hours | Rate | Total
| Running daily, weekly processes in parallel to existing system to compare results :: Estimated hours | 70 | 740 | 51800
| Project Management | 7 | 900 | 6300
| Total Cost excl VAT |  |  | 58100

## 4. Requests for Information (hidden)
Requests for Information
Record any requests for information and the answers.
Date | Question | Answered by: | Comments

## 5. Issue Log (hidden)
Risk Log
Record any risks, gaps, or issues that have occurred and how they were mitigated.
Date | Issue | Resolution | Comments

## 6. Progress Report (hidden)
Customized Progress Report
To create a customized progress report, insert the desired timeframe for analysis in the start and end date boxes below. For a progress report of the entire project, insert the project's start and end dates. Consider running reports based on the project for today, this week, or next week. IMPORTANT NOTICE: Solution owner names must be selected from the drop down menus in Tabs 2 and 3 in order for this reporting page to work correctly. If errors occur on this page, return to the BI solution tracking tab and ensure that owner names were selected from the menus, rather than typed in manually.
Enter Date to Start Progress Report | 2020-03-20 | Enter Date to End Progress Report |  | 2020-03-22
Analysis of On-Schedule Tasks to Date | Analysis of Tasks to Date |  | Analysis of Project Time Management
Task Owner | Tasks to be Completed During Specified Period | Completion Status | Scheduled Due Date | On Track Status
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF!

## Hidden (hidden)
| Variables> | "Stats" |  | Members | Date | Holiday Name
| actual | Not Yet Started | Team--> | Customer Team | 2020-03-21 | Human Rights Day | Customer Team
| completion | In Progress |  | Silicon Team | 2020-04-10 | Good Friday | Silicon Team
| status | Completed |  | Customer and Silicon Team | 2020-04-13 | Family Day | Customer and Silicon Team
|  | Cancelled |  | Unassigned | 2020-04-27 | Freedom Day | Unassigned
[5 empty] | 2020-05-01 | Worker's Day
|  |  |  | Willem Boshoff | 2020-06-16 | Youth Day | Willem Boshoff
[5 empty] | 2020-08-09 | National Women's Day
|  |  |  | Gareth Bowers | 2020-08-10 | Public Holiday | Gareth Bowers
| Status Var> | "Track" |  | Charlton Daniels | 2020-09-24 | Heritage Day | Charlton Daniels
|  | Not Yet Started |  | Heinrich Du Plessis | 2020-12-16 | Day of Reconciliation | Heinrich Du Plessis
| on track | Completed On Time |  | Cole Barnard | 2020-12-25 | Christmas Day | Cole Barnard
| completion | Completed Behind Schedule |  | Theodor Harmse | 2020-12-26 | Day of Goodwill | Theodor Harmse
| status | Completed Ahead of Schedule |  | Romano Moses |  |  | Romano Moses
|  | In Progress |  | Christopher Voges |  |  | Christopher Voges
|  | Cancelled |  | Dean Norman |  |  | Dean Norman
|  |  |  | Christine Gorgulho |  |  | Christine Gorgulho
|  |  |  | Lenetia Plage |  |  | Lenetia Plage
|  |  |  | Jessica Smith |  |  | Jessica Smith
|  |  |  | Ross Davie |  |  | Ross Davie
|  |  |  | Software Team |  |  | Software Team
0
LINK PROJECT START DATE TO THE MONDAY BEFORE (For Gantt Chart)
[16 empty] | Which wkday is it? |  |  | Find what day it is | Convert it to Monday
[13 empty] | Start Date | 2021-04-19 |  | Monday |  |  | Sunday
[13 empty] | The Monday | 2021-04-19 |  | Monday |  |  | Monday | 44305
Tuesday
Wednesday
Thursday
Friday
Saturday
#For Tab 5 - Schedule Plan
#NO WORK HOLIDAY DATES | [5 empty] | 2021-04-26
Week of | 2021-04-19 |  |  | 44308 | 44309 | 44312 | 44313 | 44314 |  |  | 2021-05-03 |  |  |  |  | 2021-05-10 |  |  |  |  | 2021-05-17 |  |  |  |  | 2021-05-24 |  |  |  |  | 2021-05-31 |  |  |  |  | 2021-06-07 |  |  |  |  | 2021-06-14 |  |  |  |  | 2021-06-21 |  |  |  |  | 2021-06-28 |  |  |  |  | 2021-07-05 |  |  |  |  | 2021-07-12 |  |  |  |  | 2021-07-19 |  |  |  |  | 2021-07-26 |  |  |  |  | 2021-08-02 |  |  |  |  | 2021-08-09 |  |  |  |  | 2021-08-16 |  |  |  |  | 2021-08-23 |  |  |  |  | 2021-08-30 |  |  |  |  | 2021-09-06 |  |  |  |  | 2021-09-13 |  |  |  |  | 2021-09-20 |  |  |  |  | 2021-09-27 |  |  |  |  | 2021-10-04 |  |  |  |  | 2021-10-11 |  |  |  |  | 2021-10-18 |  |  |  |  | 2021-10-25 |  |  |  |  | 2021-11-01 |  |  |  |  | 2021-11-08 |  |  |  |  | 2021-11-15 |  |  |  |  | 2021-11-22 |  |  |  |  | 2021-11-29 |  |  |  |  | 2021-12-06 |  |  |  |  | 2021-12-13 |  |  |  |  | 2021-12-20 |  |  |  |  | 2021-12-27 |  |  |  |  | 2022-01-03 |  |  |  |  | 2022-01-10 |  |  |  |  | 2022-01-17 |  |  |  |  | 2022-01-24 |  |  |  |  | 2022-01-31 |  |  |  |  | 2022-02-07 |  |  |  |  | 2022-02-14 |  |  |  |  | 2022-02-21 |  |  |  |  | 2022-02-28 |  |  |  |  | 2022-03-07 |  |  |  |  | 2022-03-14 |  |  |  |  | 2022-03-21 |  |  |  |  | 2022-03-28 |  |  |  |  | 2022-04-04 |  |  |  |  | 2022-04-11 |  |  |  |  | 2022-04-18 |  |  |  |  | 2022-04-25
Day Date | 44305 | 44306 | 44307 | No | No | No | No | No |  |  | 44319 | 44320 | 44321 | 44322 | 44323 | 44326 | 44327 | 44328 | 44329 | 44330 | 44333 | 44334 | 44335 | 44336 | 44337 | 44340 | 44341 | 44342 | 44343 | 44344 | 44347 | 44348 | 44349 | 44350 | 44351 | 44354 | 44355 | 44356 | 44357 | 44358 | 44361 | 44362 | 44363 | 44364 | 44365 | 44368 | 44369 | 44370 | 44371 | 44372 | 44375 | 44376 | 44377 | 44378 | 44379 | 44382 | 44383 | 44384 | 44385 | 44386 | 44389 | 44390 | 44391 | 44392 | 44393 | 44396 | 44397 | 44398 | 44399 | 44400 | 44403 | 44404 | 44405 | 44406 | 44407 | 44410 | 44411 | 44412 | 44413 | 44414 | 44417 | 44418 | 44419 | 44420 | 44421 | 44424 | 44425 | 44426 | 44427 | 44428 | 44431 | 44432 | 44433 | 44434 | 44435 | 44438 | 44439 | 44440 | 44441 | 44442 | 44445 | 44446 | 44447 | 44448 | 44449 | 44452 | 44453 | 44454 | 44455 | 44456 | 44459 | 44460 | 44461 | 44462 | 44463 | 44466 | 44467 | 44468 | 44469 | 44470 | 44473 | 44474 | 44475 | 44476 | 44477 | 44480 | 44481 | 44482 | 44483 | 44484 | 44487 | 44488 | 44489 | 44490 | 44491 | 44494 | 44495 | 44496 | 44497 | 44498 | 44501 | 44502 | 44503 | 44504 | 44505 | 44508 | 44509 | 44510 | 44511 | 44512 | 44515 | 44516 | 44517 | 44518 | 44519 | 44522 | 44523 | 44524 | 44525 | 44526 | 44529 | 44530 | 44531 | 44532 | 44533 | 44536 | 44537 | 44538 | 44539 | 44540 | 44543 | 44544 | 44545 | 44546 | 44547 | 44550 | 44551 | 44552 | 44553 | 44554 | 44557 | 44558 | 44559 | 44560 | 44561 | 44564 | 44565 | 44566 | 44567 | 44568 | 44571 | 44572 | 44573 | 44574 | 44575 | 44578 | 44579 | 44580 | 44581 | 44582 | 44585 | 44586 | 44587 | 44588 | 44589 | 44592 | 44593 | 44594 | 44595 | 44596 | 44599 | 44600 | 44601 | 44602 | 44603 | 44606 | 44607 | 44608 | 44609 | 44610 | 44613 | 44614 | 44615 | 44616 | 44617 | 44620 | 44621 | 44622 | 44623 | 44624 | 44627 | 44628 | 44629 | 44630 | 44631 | 44634 | 44635 | 44636 | 44637 | 44638 | 44641 | 44642 | 44643 | 44644 | 44645 | 44648 | 44649 | 44650 | 44651 | 44652 | 44655 | 44656 | 44657 | 44658 | 44659 | 44662 | 44663 | 44664 | 44665 | 44666 | 44669 | 44670 | 44671 | 44672 | 44673 | 44676 | 44677 | 44678 | 44679 | 44680
HOLIDAY? | No | No | No | [5 empty] | 44315 | 44316 | bar: 2021-05-03 44319 to 2022-04-25 44680
43911 | [8 empty] | No | No
43931
43934
43948
43952
43998
44052
44053
44098
44181
44190
44191
0
0
0
0
For Pie chart 2 in Today's View - TOTAL PROJECT
|  |  |  | Today | 2022-02-17 | CODE TASKS FOR THIS WEEK…. Ugh/ |  | Tasks Completed |  |  | 2021-05-03 44320: For Pie chart 1 in Today - Today's Recommendations; 2021-05-10 44326: For Time Line in Today; 2021-05-10 44329: Not subtracting weekends & holidays…; 2021-05-24 44340: Recommendation is underway but is behind schedule.
[8 empty] | Tasks In Progress |  |  | 2021-05-03 44320: Behind Schedule Tasks - Started; 2021-05-03 44321: 0; 2021-05-10 44326: Project Start; 2021-05-10 44327: 44305; 2021-05-10 44329: Allocated Days Passed; 2021-05-10 44330: 304; 2021-05-17 44333: 84.21%; 2021-05-24 44340: Recommendation is late and has not yet been started.
[8 empty] | Tasks Not Yet Started | 20.45% |  | 2021-05-03 44320: Behind Schedule Tasks - Not Yet Started; 2021-05-03 44321: 0; 2021-05-10 44326: Today; 2021-05-10 44327: 44609; 2021-05-10 44329: Allocated Days Left; 2021-05-10 44330: 57; 2021-05-17 44333: 15.79%
|  | AMOUNT | of valid tasks |  | Total Tasks | 88 |  |  | 0% |  | 2021-05-03 44320: Regularly Scheduled Tasks; 2021-05-03 44321: 0; 2021-05-10 44326: Project End; 2021-05-10 44327: 44666
|  | 14 | [5 empty] | QC | 90.91% |  | 2021-05-03 44320: QC; 2021-05-03 44321: 0; 2021-05-10 44329: QC; 2021-05-10 44330: 361
361
111.4%
Note on N34: From user input
Note on N35: The Monday of the first week of project commencement...

## HiddenWkly (hidden)
"Weekly" (or whatever) task view | [10 empty] | Task Not Yet Started |  |  | Task is underway but is behind schedule.
[11 empty] | Task Complete |  |  | Task is late and has not yet been started.
start date entry | 2020-03-20 | 43910 | [8 empty] | Task In Progress |  |  | Task is scheduled for work during this timeframe.
End date entry | 2020-03-22 | 43912
Today | 2022-02-17 | 44609
[26 empty] | TO ORDER BY RECOMMENDATION OWNER |  |  |  |  | Actual list for Tab
TASK NUMBER | ID for Task | "Rank" to list | Repeat Task for VLOOKUP | TASK | Estimated Start Date | Estimated End Date | Owner | Owner for List | Actual Start Date | Actual End Date |  | On Track Status | Task should be done - Started | Task Should be done - Not Yet Started | Reg Scheduled Task during this time | Sum | Unique Rank for Owners, by task | Owner Rank | Task Owner | List of Tasks | Task Name | Est Start Date | Est End Date - DUE DATE | Completion Status | On Track Status | Possible Owner | Task Number | Yes to task | Unique Rank |  | RANK | Owner | Owner for Tab | Task | Task Status | Due Date | Completion Status
1 |  |  |  | Proposal Planning Phase |  |  |  | Unassigned |  |  | Task Not Yet Started |  | No | No | No | 1 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | Unassigned | 0 |  |  | Customer Team | 1 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
2 |  |  |  | Discuss, discover, analyze, and prioritize application and data centre resource portfolios for migration with the customer | 2021-04-19 | 2021-05-13 | Customer and Silicon Team | Customer and Silicon Team | 2021-04-19 | 2021-05-13 | Task Complete |  | No | No | No | 3 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | Customer Team | 0 |  |  | Silicon Team | 2 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
3 |  |  |  | Document discovered resources, dependencies, and usage data | 2021-04-19 | 2021-05-13 | Silicon Team | Silicon Team | 2021-04-19 | 2021-05-13 | Task Complete |  | No | No | No | 6 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | Silicon Team | 0 |  |  | Customer and Silicon Team | 3 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
4 |  |  |  | Document a prioritized list of applications and workloads for migration | 2021-04-19 | 2021-05-13 | Silicon Team | Silicon Team | 2021-04-19 | 2021-05-13 | Task Complete |  | No | No | No | 10 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | Customer and Silicon Team | 0 |  |  | Unassigned | 4 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
5 |  |  |  | Assess and design an initial AWS account structure. Assess AWS Organizations or Landing Zone for suitability | 2021-04-19 | 2021-05-13 | Silicon Team | Silicon Team | 2021-04-19 | 2021-05-13 | Task Complete |  | No | No | No | 15 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | Unassigned | 0 |  |  | 0 | 5 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
6 | [14 empty] | No | 21 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0 |  |  |  | Willem Boshoff | 6 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
7 |  |  |  | Proposal Design Phase |  |  |  | Unassigned |  |  | Task Not Yet Started |  | No | No | No | 28 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | Willem Boshoff | 0 |  |  | 0 | 7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
8 |  |  |  | Determine migration method – Re-host, Re-platform, Re-factor, Re-purchase, Retain, or Retire | 2021-05-13 | 2021-06-07 | Silicon Team | Silicon Team | 2021-05-13 | 2021-06-07 | Task Complete |  | No | No | No | 36 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0 |  |  |  | Gareth Bowers | 8 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
9 |  |  |  | Discuss with customer and specify migration target requirements (security, reliability, scaling, performance, monitoring, deployment automation, RTO, RPO etc.) | 2021-05-13 | 2021-06-07 | Silicon Team | Silicon Team | 2021-05-13 | 2021-06-07 | Task Complete |  | No | No | No | 45 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | Gareth Bowers | 0 |  |  | Charlton Daniels | 9 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
10 |  |  |  | Create a Migration Proposal. Based on the above and the account structure defined in the Planning Phase, design the AWS Best Practice Architecture with architectural diagrams; address the requirements using the AWS Well-Architected Framework covering security, reliability, performance efficiency, cost optimization, and operations excellence. Create cost estimates using the AWS Pricing Calculator. Assess eligible AWS funding programs to access usage and or migration funding for the customer. Estimate project hours to deliver the project based on the Architecture and Project Scope. Evaluate and select migration tools or method. Document deliverables. | 2021-05-13 | 2021-06-07 | Silicon Team | Silicon Team | 2021-05-13 | 2021-06-07 | Task Complete |  | No | No | No | 55 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | Charlton Daniels | 0 |  |  | Heinrich Du Plessis | 10 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
11 | [14 empty] | No | 66 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | Heinrich Du Plessis | 0 |  |  | Cole Barnard | 11 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
12 |  |  |  | Project Proposal Authorisation Phase |  |  |  | Unassigned |  |  | Task Not Yet Started |  | No | No | No | 78 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | Cole Barnard | 0 |  |  | Theodor Harmse | 12 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
13 |  |  |  | Present and discuss the Proposal with the customer. Select and sign off the architecture, AWS pricing estimates, AWS Marketplace pricing estimates, AWS funding, scope, our professional services pricing estimates and timeline. Discuss the AWS Pricing Calculator limitations, security guidelines, cost optimization process and project planning phases. Present AWS account linking and CloudHealth benefits. Present Trend Cloud Conformity pricing. | 2021-06-07 | 2021-07-15 | Silicon Team | Silicon Team | 2021-06-07 | 2021-07-15 | Task Complete |  | No | No | No | 91 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | Theodor Harmse | 0 |  |  | Romano Moses | 13 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
14 |  |  |  | Finalise the Proposal in discussion with the customer | 2021-06-07 | 2021-07-15 | Silicon Team | Silicon Team | 2021-06-07 | 2021-07-15 | Task Complete |  | No | No | No | 105 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | Romano Moses | 0 |  |  | Christopher Voges | 14 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
15 |  |  |  | Authorize AWS account linking and CloudHealth free of charge. | 2021-06-07 | 2021-07-15 | Customer Team | Customer Team | 2021-06-07 | 2021-07-15 | Task Complete |  | No | No | No | 120 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | Christopher Voges | 0 |  |  | Dean Norman | 15 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
16 |  |  |  | Authorize Trend Cloud Conformity on an annual basis, billed monthly |  |  | Customer Team | Customer Team |  |  | Task Not Yet Started |  | No | No | No | 136 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | Dean Norman | 0 |  |  | Christine Gorgulho | 16 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
17 |  |  |  | Customer to initial all pages and sign the Proposal | 2021-07-15 | 2021-07-15 | Customer Team | Customer Team | 2021-07-15 | 2021-07-15 | Task Complete |  | No | No | No | 153 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | Christine Gorgulho | 0 |  |  | Lenetia Plage | 17 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
18 | [14 empty] | No | 171 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | Lenetia Plage | 0 |  |  | Jessica Smith | 18 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
19 |  |  |  | AWS Account Linking and Cost Optimization Reporting: Link account/s for cost and AWS credit benefits and setup CloudHealth reporting and alerting for rightsizing, alerting and cost optimization reporting. |  |  |  | Unassigned |  |  | Task Not Yet Started |  | No | No | No | 190 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | Jessica Smith | 0 |  |  | Ross Davie | 19 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
20 |  |  |  | Link your AWS account | 2021-07-15 | 2021-09-20 | Silicon Team | Silicon Team | 2021-07-15 | 2021-09-20 | Task Complete |  | No | No | No | 210 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | Ross Davie | 0 |  |  | Software Team | 20 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
21 |  |  |  | Link your AWS account to CloudHealth | 2021-07-15 | 2021-09-20 | Silicon Team | Silicon Team | 2021-07-15 | 2021-09-20 | Task Complete |  | No | No | No | 231 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | Software Team | 0 |  |  | 0 | 21 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
22 |  |  |  | Setup automated CloudHealth reporting: Cost Optimisation Opportunities, Cloud Governance, Operational Monthly Savings, Security Risk Exposure, Rightsizing Recommendations, Reserved Instance reporting | 2021-07-15 | 2021-09-20 | Silicon Team | Silicon Team | 2021-07-15 | 2021-09-20 | Task Complete |  | No | No | No | 253 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0 |  |  |  | 0 | 22 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
23 |  |  |  | Setup access to CloudHealth Console | 2021-07-15 | 2021-09-20 | Silicon Team | Silicon Team | 2021-07-15 | 2021-09-20 | Task Complete |  | No | No | No | 276 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0 |  |  |  | 0 | 23 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
24 |  |  |  | Basic CloudHealth training | 2021-07-15 | 2021-09-20 | Silicon Team | Silicon Team | 2021-07-15 | 2021-09-20 | Task Complete |  | No | No | No | 300 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0 |  |  |  | 0 | 24 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
25 | [14 empty] | No | 325 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0 |  |  |  | 0 | 25 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
26 |  |  |  | AWS Funding Application |  |  |  | Unassigned |  |  | Task Not Yet Started |  | No | No | No | 351 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0 |  |  |  | 0 | 26 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
27 |  |  |  | Generate the AWS funding application documentation based on the finalised proposal authorized by the customer. Submit to appropriate AWS program | 2021-07-15 | 2021-09-20 | Silicon Team | Silicon Team | 2021-07-15 | 2021-09-20 | Task Complete |  | No | No | No | 378 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0 |  |  |  | 0 | 27 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
28 |  |  |  | On AWS funding approval, update the Proposal the reflect the funding achieved. | 2021-09-20 | 2021-09-20 | Silicon Team | Silicon Team | 2021-09-20 | 2021-09-20 | Task Complete |  | No | No | No | 406 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0 |  |  |  | 0 | 28 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
29 | [14 empty] | No | 435 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0 |  |  |  | 0 | 29 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
30 |  |  |  | Project Plan Phase |  |  |  | Unassigned |  |  | Task Not Yet Started |  | No | No | No | 465 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0 |  |  |  | 0 | 30 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
31 |  |  |  | Generate the Project Plan including stakeholders and participants, work schedule and task owners | 2021-09-20 |  | Silicon Team | Silicon Team |  |  | Task Not Yet Started |  | No | No | No | 496 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0 |  |  |  | 0 | 31 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
32 |  |  |  | Refine and finalise the project plan in discussion |  |  | Customer and Silicon Team | Customer and Silicon Team |  |  | Task Not Yet Started |  | No | No | No | 528 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0 |  |  |  | 0 | 32 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
33 | [14 empty] | No | 561 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0 |  |  |  | 0 | 33 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
34 |  |  |  | Migration Phase |  |  |  | Unassigned |  |  | Task Not Yet Started |  | No | No | No | 595 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0 |  |  |  | 0 | 34 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
35 |  |  |  | Account 1 - AWS Production Environment with React.js Web Applications, Glue, QuickSight and Multi-AZ Aurora MySQL Databases |  |  |  | Unassigned |  |  | Task Not Yet Started |  | No | No | No | 630 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0 |  |  |  | 0 | 35 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
36 |  |  |  | Setup base account configuration as per AWS Best Practices including secure IAM setup and virtual MFA, disable Regions not in use, account information setup etc. |  |  | Silicon Team | Silicon Team |  |  | Task Not Yet Started |  | No | No | No | 666 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0 |  |  |  | 0 | 36 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
37 |  |  |  | Setup cost Alerts and weekly Reports based on the Proposal monthly AWS cost estimates in CloudHealth or AWS Budgets. Setup 50% and 100% Actual and 50%, 100%, 150% Forecasted alerts and include project teams. Alerts and reports to be sent to: awsbudgetalerts@overdrive.co.za Customer to setup awsbudgetalerts@ mail address and forward to team monitoring the AWs budgets and costs. The customer must monitor these budget and cost alerts. |  |  | Silicon Team | Silicon Team |  |  | Task Not Yet Started |  | No | No | No | 703 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0 |  |  |  | 0 | 37 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
38 |  |  |  | On authorization setup Trend Cloud Conformity on an annual subscription, billed monthly |  |  | Silicon Team | Silicon Team |  |  | Task Not Yet Started |  | No | No | No | 741 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0 |  |  |  | 0 | 38 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
39 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 780 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0 |  |  |  | 0 | 39 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
40 |  |  |  | Configure AWS Services as per authorised Architecture |  |  |  | Unassigned |  |  | Task Not Yet Started |  | No | No | No | 820 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0 |  |  |  | 0 | 40 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
41 |  |  |  | Conduct a security and AWS best practice validation using Cloud Conformity with reporting, and or a manual design and architecture validation assessment report. Implement any outstanding requirements. Re-run the validation reporting process. |  |  | Silicon Team | Silicon Team |  |  | Task Not Yet Started |  | No | No | No | 861 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0 |  |  |  | 0 | 41 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
42 |  |  |  | Schedule a handover meeting with project teams |  |  | Silicon Team | Silicon Team |  |  | Task Not Yet Started |  | No | No | No | 903 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [5 empty] | 42 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
43 |  |  |  | Integrate the migrated workloads (application servers, databases, data, or infrastructure services) with the AWS environment and services |  |  | Customer Team | Customer Team |  |  | Task Not Yet Started |  | No | No | No | 946 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [5 empty] | 43 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
44 |  |  |  | Customer application testing phase |  |  | Customer Team | Customer Team |  |  | Task Not Yet Started |  | No | No | No | 990 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [5 empty] | 44 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
45 |  |  |  | Customer application load testing phase. Customer procured load testing tools may include K6/Load Impact, Gremlin etc. |  |  | Customer Team | Customer Team |  |  | Task Not Yet Started |  | No | No | No | 1035 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [5 empty] | 45 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
46 |  |  |  | Perform cutover to the migrated services with a customer designed rollback plan |  |  | Customer Team | Customer Team |  |  | Task Not Yet Started |  | No | No | No | 1081 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [5 empty] | 46 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
47 |  |  |  | Customer satisfaction checkpoint - send CSAT Deliverables: Migrated applications and workloads validated and running in the production environment in AWS |  |  | Silicon Team | Silicon Team |  |  | Task Not Yet Started |  | No | No | No | 1128 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [5 empty] | 47 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
48 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 1176 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [5 empty] | 48 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
49 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 1225 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [5 empty] | 49 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
50 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 1275 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [5 empty] | 50 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
51 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 1326 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [5 empty] | 51 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
52 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 1378 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [5 empty] | 52 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
53 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 1431 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [5 empty] | 53 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
54 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 1485 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [5 empty] | 54 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
55 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 1540 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [5 empty] | 55 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
56 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 1596 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [5 empty] | 56 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
57 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 1653 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [5 empty] | 57 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
58 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 1711 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [5 empty] | 58 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
59 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 1770 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [5 empty] | 59 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
60 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 1830 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [5 empty] | 60 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
61 | [14 empty] | No | 1891 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [5 empty] | 61 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
62 |  |  |  | Best Practice Pre-Go Live Recommendations It is Best Practice to: |  |  |  | Unassigned |  |  | Task Not Yet Started |  | No | No | No | 1953 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [5 empty] | 62 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
63 |  |  |  | Setup Trend Cloud Conformity for security and governance alerts and reporting. Run a security and compliance assessment report. Remediate and implement any improvements. Re-run a security and compliance assessment report for improvement validation. |  |  | Silicon Team | Silicon Team |  |  | Task Not Yet Started |  | No | No | No | 2016 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [5 empty] | 63 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
64 |  |  |  | If Cloud Conformity not authorized conduct an AWS Security and Best Practice validation assessment for each account. Remediate and implement limited improvements. Re-conduct the AWS Security and Best Practice validation assessment for each account. |  |  | Silicon Team | Silicon Team |  |  | Task Not Yet Started |  | No | No | No | 2080 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [5 empty] | 64 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
65 |  |  |  | Implement Amazon CloudWatch Dashboard for monitoring. Implement alerting for project teams |  |  | Silicon Team | Silicon Team |  |  | Task Not Yet Started |  | No | No | No | 2145 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [5 empty] | 65 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
66 |  |  |  | Setup AWS Backup Using AWS Backup, you can centrally configure backup policies and monitor backup activity for AWS resources, such as Amazon EBS volumes, Amazon RDS databases, Amazon DynamoDB tables, Amazon EFS file systems, AWS Storage Gateway volumes. |  |  | Silicon Team | Silicon Team |  |  | Task Not Yet Started |  | No | No | No | 2211 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [5 empty] | 66 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
67 |  |  |  | Enable Versioning on all important and Production Amazon S3 Buckets |  |  | Silicon Team | Silicon Team |  |  | Task Not Yet Started |  | No | No | No | 2278 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [5 empty] | 67 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
68 |  |  |  | Generate a provisional DR, Backup and Restore Policy |  |  | Silicon Team | Silicon Team |  |  | Task Not Yet Started |  | No | No | No | 2346 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [5 empty] | 68 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
69 |  |  |  | Check and redeem all remaining AWS credits |  |  | Silicon Team | Silicon Team |  |  | Task Not Yet Started |  | No | No | No | 2415 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [5 empty] | 69 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
70 | [14 empty] | No | 2485 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [5 empty] | 70 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
71 |  |  |  | Preliminary Optimization Phase |  |  |  | Unassigned |  |  | Task Not Yet Started |  | No | No | No | 2556 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [5 empty] | 71 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
72 |  |  |  | Conduct an initial, basic Cost Optimization assessment and present any recommendations for later implementation (e.g. obvious rightsizing opportunities, using Reserved Instances or AWS Savings Plans). Generally workloads need to run for one to three months in production before a baseline can be understood for cost optimization. |  |  | Silicon Team | Silicon Team |  |  | Task Not Yet Started |  | No | No | No | 2628 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [5 empty] | 72 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
73 |  |  |  | Present the assessment findings via email or on a call |  |  | Silicon Team | Silicon Team |  |  | Task Not Yet Started |  | No | No | No | 2701 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [5 empty] | 73 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
74 |  |  |  | Update AWS Budgets and AWS Budget Reports |  |  | Silicon Team | Silicon Team |  |  | Task Not Yet Started |  | No | No | No | 2775 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [5 empty] | 74 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
75 |  |  |  | If not already implemented and if applicable: Implement AWS Systems Manager Agent (SSM Agent) to automate EC2 Patch Management to reduce the Maintenance Agreement. Implement Amazon Inspector Agent. |  |  | Silicon Team | Silicon Team |  |  | Task Not Yet Started |  | No | No | No | 2850 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [5 empty] | 75 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
76 | [14 empty] | No | 2926 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [5 empty] | 76 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
77 |  |  |  | Project Closure Phase |  |  |  | Unassigned |  |  | Task Not Yet Started |  | No | No | No | 3003 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [5 empty] | 77 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
78 |  |  |  | Provide limited training about the AWS environment running migrated or deployed applications to the customer |  |  | Silicon Team | Silicon Team |  |  | Task Not Yet Started |  | No | No | No | 3081 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [5 empty] | 78 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
79 |  |  |  | Handover the final architecture diagrams, implementation notes, and DR Backup and Restore Policy |  |  | Silicon Team | Silicon Team |  |  | Task Not Yet Started |  | No | No | No | 3160 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [5 empty] | 79 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
80 |  |  |  | Email the AWS POA Customer Sign‐Off Template |  |  | Silicon Team | Silicon Team |  |  | Task Not Yet Started |  | No | No | No | 3240 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [5 empty] | 80 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
81 |  |  |  | Sign the AWS POA Customer Sign‐Off Template with Project Deliverables |  |  | Customer Team | Customer Team |  |  | Task Not Yet Started |  | No | No | No | 3321 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [5 empty] | 81 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
82 |  |  |  | Complete the AWS Customer Satisfaction Survey (CSAT) and notify the Silicon projects team once completed |  |  | Customer Team | Customer Team |  |  | Task Not Yet Started |  | No | No | No | 3403 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [5 empty] | 82 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
83 | [14 empty] | No | 3486 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [5 empty] | 83 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
84 |  |  |  | Optional Trend Cloud Conformity |  |  |  | Unassigned |  |  | Task Not Yet Started |  | No | No | No | 3570 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [5 empty] | 84 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
85 |  |  |  | Link your AWS account |  |  | Silicon Team | Silicon Team |  |  | Task Not Yet Started |  | No | No | No | 3655 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [5 empty] | 85 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
86 |  |  |  | Setup automated Cloud Conformity security and governance reporting and alerting |  |  | Silicon Team | Silicon Team |  |  | Task Not Yet Started |  | No | No | No | 3741 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [5 empty] | 86 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
87 |  |  |  | Setup access to Cloud Conformity Console |  |  | Silicon Team | Silicon Team |  |  | Task Not Yet Started |  | No | No | No | 3828 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [5 empty] | 87 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
88 |  |  |  | Basic Cloud Conformity training |  |  | Silicon Team | Silicon Team |  |  | Task Not Yet Started |  | No | No | No | 3916 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [5 empty] | 88 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
89 | [14 empty] | No | 4005 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [5 empty] | 89 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
90 |  |  |  | Optional Post-Migration Optimization Phase |  |  |  | Unassigned |  |  | Task Not Yet Started |  | No | No | No | 4095 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [5 empty] | 90 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
91 |  |  |  | Conduct a full Cost Optimization assessment and present any recommendations for implementation (e.g. rightsizing EC2, using Reserved Instances or AWS Savings Plans) |  |  | Silicon Team | Silicon Team |  |  | Task Not Yet Started |  | No | No | No | 4186 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [5 empty] | 91 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
92 |  |  |  | Present the assessment findings on a call |  |  | Silicon Team | Silicon Team |  |  | Task Not Yet Started |  | No | No | No | 4278 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [5 empty] | 92 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
93 |  |  |  | Update AWS Budgets and AWS Budget Reports |  |  | Silicon Team | Silicon Team |  |  | Task Not Yet Started |  | No | No | No | 4371 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [5 empty] | 93 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
94 |  |  |  | If not already implemented and if applicable: Implement AWS Systems Manager Agent (SSM Agent) to automate EC2 Patch Management to reduce the Maintenance Agreement. Implement Amazon Inspector Agent. |  |  | Silicon Team | Silicon Team |  |  | Task Not Yet Started |  | No | No | No | 4465 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [5 empty] | 94 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
95 |  |  |  | Run a Trend Cloud Conformity security and compliance assessment report. Remediate and implement any improvements. Re-run a security and compliance assessment report for improvement validation. |  |  | Silicon Team | Silicon Team |  |  | Task Not Yet Started |  | No | No | No | 4560 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [5 empty] | 95 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
96 |  |  |  | Customer satisfaction checkpoint - send CSAT |  |  | Silicon Team | Silicon Team |  |  | Task Not Yet Started |  | No | No | No | 4656 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [5 empty] | 96 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
97 | [14 empty] | No | 4753 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [5 empty] | 97 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
98 |  |  |  | Optional Support and Maintenance (Operations) Phase |  |  |  | Unassigned |  |  | Task Not Yet Started |  | No | No | No | 4851 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [5 empty] | 98 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
99 |  |  |  | Provide ongoing AWS support and AWS and security maintenance under agreement to meet requirements, including operations, security and cost optimization tasks. |  |  | Silicon Team | Silicon Team |  |  | Task Not Yet Started |  | No | No | No | 4950 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [5 empty] | 99 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
100 |  |  |  | Access to support and our AWS team would be on an Agreement basis for several business, continuity and service delivery reasons. |  |  |  | Unassigned |  |  | Task Not Yet Started |  | No | No | No | 5050 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [5 empty] | 100 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
101 | [14 empty] | No | 5151 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [5 empty] | 101 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
102 |  |  |  | AWS, server and security maintenance |  |  | Silicon Team | Silicon Team |  |  | Task Not Yet Started |  | No | No | No | 5253 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [5 empty] | 102 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
103 |  |  |  | Trend Cloud Conformity automated security and governance reporting and alerting |  |  | Silicon Team | Silicon Team |  |  | Task Not Yet Started |  | No | No | No | 5356 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [5 empty] | 103 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
104 |  |  |  | Monitoring and alerting |  |  | Silicon Team | Silicon Team |  |  | Task Not Yet Started |  | No | No | No | 5460 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [5 empty] | 104 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
105 |  |  |  | Review logs |  |  | Silicon Team | Silicon Team |  |  | Task Not Yet Started |  | No | No | No | 5565 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [5 empty] | 105 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
106 |  |  |  | Backup monitoring |  |  | Silicon Team | Silicon Team |  |  | Task Not Yet Started |  | No | No | No | 5671 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [5 empty] | 106 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
107 |  |  |  | System and Security patch management |  |  | Silicon Team | Silicon Team |  |  | Task Not Yet Started |  | No | No | No | 5778 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [5 empty] | 107 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
108 |  |  |  | Support, troubleshooting and escalation procedures |  |  | Customer and Silicon Team | Customer and Silicon Team |  |  | Task Not Yet Started |  | No | No | No | 5886 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [5 empty] | 108 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
109 |  |  |  | Change management |  |  | Customer Team | Customer Team |  |  | Task Not Yet Started |  | No | No | No | 5995 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [5 empty] | 109 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
110 | [14 empty] | No | 6105 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [5 empty] | 110 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
111 |  |  |  | Cost optimization reviews |  |  | Customer and Silicon Team | Customer and Silicon Team |  |  | Task Not Yet Started |  | No | No | No | 6216 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [5 empty] | 111 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
112 |  |  |  | Operational optimization reviews |  |  | Customer and Silicon Team | Customer and Silicon Team |  |  | Task Not Yet Started |  | No | No | No | 6328 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [5 empty] | 112 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
113 | [14 empty] | No | 6441 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [5 empty] | 113 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
114 |  |  |  | Conduct annual AWS and security best practice validation assessments |  |  | Silicon Team | Silicon Team |  |  | Task Not Yet Started |  | No | No | No | 6555 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [5 empty] | 114 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
115 |  |  |  | Conduct annual AWS Cost Optimization assessments |  |  | Silicon Team | Silicon Team |  |  | Task Not Yet Started |  | No | No | No | 6670 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [5 empty] | 115 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
116 | [14 empty] | No | 6786 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [5 empty] | 116 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
117 |  |  |  | Optional AWS Well-Architected Review Phase AWS Well-Architected Review per workload - evaluate the current architectures and implement operational excellence, security, reliability, performance efficiency, and cost optimization improvements. In this process AWS will provide you with $5000 in service credits if you leverage an approved AWS Well-Architected Partner, like us, to help improve the workload. |  |  |  | Unassigned |  |  | Task Not Yet Started |  | No | No | No | 6903 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [5 empty] | 117 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
118 |  |  |  | Run a Trend Cloud Conformity security and compliance assessment report in preparation for, and before we conduct the AWS Well-Architected Review. |  |  | Silicon Team | Silicon Team |  |  | Task Not Yet Started |  | No | No | No | 7021 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [5 empty] | 118 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
119 |  |  |  | If Trend Cloud Conformity not authorized conduct an AWS Security and Best Practice assessment in preparation for, and before we conduct the AWS Well-Architected Review |  |  | Silicon Team | Silicon Team |  |  | Task Not Yet Started |  | No | No | No | 7140 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [5 empty] | 119 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
120 |  |  |  | Conduct the AWS Well-Architected Review. |  |  | Silicon Team | Silicon Team |  |  | Task Not Yet Started |  | No | No | No | 7260 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [5 empty] | 120 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
121 |  |  |  | Generate a provisional Project Plan with high risk remediations to be implemented |  |  | Silicon Team | Silicon Team |  |  | Task Not Yet Started |  | No | No | No | 7381 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [5 empty] | 121 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
122 |  |  |  | Select and assign task owners for remediations. |  |  | Customer Team | Customer Team |  |  | Task Not Yet Started |  | No | No | No | 7503 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [5 empty] | 122 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
123 |  |  |  | Submit a proposal based on the customer selected remediations and tasks assigned to the Silicon Team for remediation or implementation |  |  | Customer Team | Customer Team |  |  | Task Not Yet Started |  | No | No | No | 7626 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [5 empty] | 123 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
124 |  |  |  | Authorise the Proposal to be submitted |  |  | Customer Team | Customer Team |  |  | Task Not Yet Started |  | No | No | No | 7750 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [5 empty] | 124 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
125 |  |  |  | Implement any priority Assessment and AWS Well-Architected Review and Recommendations and Improvements. Paid Improvements must start no later than 30 days after the review. |  |  | Customer and Silicon Team | Customer and Silicon Team |  |  | Task Not Yet Started |  | No | No | No | 7875 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [5 empty] | 125 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
126 |  |  |  | Submit the AWS Well-Architected Review remediations milestone update to AWS. AWS requires a minimum of 25% of the HRI (high risk items) to be remediated by us before we submit this milestone update to apply for the credits |  |  | Silicon Team | Silicon Team |  |  | Task Not Yet Started |  | No | No | No | 8001 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [5 empty] | 126 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
127 |  |  |  | Complete the AWS Customer Satisfaction Survey (CSAT) once emailed by AWS, and notify the Silicon projects team once completed |  |  | Customer Team | Customer Team |  |  | Task Not Yet Started |  | No | No | No | 8128 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [5 empty] | 127 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
128 |  |  |  | Apply the $5000 credits to one of your AWS accounts once AWS emails you the promo credit code. |  |  | Customer Team | Customer Team |  |  | Task Not Yet Started |  | No | No | No | 8256 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [5 empty] | 128 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
129 | [14 empty] | No | 8385 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [5 empty] | 129 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
130 | [14 empty] | No | 8515 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [5 empty] | 130 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
131 | [14 empty] | No | 8646 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [5 empty] | 131 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
132 | [14 empty] | No | 8778 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [5 empty] | 132 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
133 | [14 empty] | No | 8911 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [5 empty] | 133 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
134 | [14 empty] | No | 9045 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [5 empty] | 134 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
135 | [14 empty] | No | 9180 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [5 empty] | 135 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
136 | [14 empty] | No | 9316 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [5 empty] | 136 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
137 | [14 empty] | No | 9453 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [5 empty] | 137 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
138 | [14 empty] | No | 9591 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [5 empty] | 138 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
139 | [14 empty] | No | 9730 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [5 empty] | 139 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
140 | [14 empty] | No | 9870 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [5 empty] | 140 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
141 | [14 empty] | No | 10011 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [5 empty] | 141 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
142 | [14 empty] | No | 10153 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [5 empty] | 142 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
143 | [14 empty] | No | 10296 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [5 empty] | 143 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
144 | [14 empty] | No | 10440 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [5 empty] | 144 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
145 | [14 empty] | No | 10585 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [5 empty] | 145 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
146 | [14 empty] | No | 10731 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [5 empty] | 146 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
147 | [14 empty] | No | 10878 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [5 empty] | 147 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
148 | [14 empty] | No | 11026 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [5 empty] | 148 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
149 | [14 empty] | No | 11175 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [5 empty] | 149 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
150 | [14 empty] | No | 11325 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [5 empty] | 150 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
151 | [14 empty] | No | 11476 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [5 empty] | 151 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
152 | [14 empty] | No | 11628 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [5 empty] | 152 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
153 | [14 empty] | No | 11781 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [5 empty] | 153 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
154 | [14 empty] | No | 11935 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [5 empty] | 154 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
155 | [14 empty] | No | 12090 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [5 empty] | 155 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
156 | [14 empty] | No | 12246 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [5 empty] | 156 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
157 | [14 empty] | No | 12403 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [5 empty] | 157 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
158 | [14 empty] | No | 12561 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [5 empty] | 158 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
159 | [14 empty] | No | 12720 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [5 empty] | 159 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
160 | [14 empty] | No | 12880 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [5 empty] | 160 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
161 | [14 empty] | No | 13041 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [5 empty] | 161 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
162 | [14 empty] | No | 13203 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [5 empty] | 162 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
163 | [14 empty] | No | 13366 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [5 empty] | 163 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
164 | [14 empty] | No | 13530 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [5 empty] | 164 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
165 | [14 empty] | No | 13695 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [5 empty] | 165 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
166 | [14 empty] | No | 13861 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [5 empty] | 166 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
167 | [14 empty] | No | 14028 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [5 empty] | 167 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
168 | [14 empty] | No | 14196 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [5 empty] | 168 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
169 | [14 empty] | No | 14365 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [5 empty] | 169 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
170 | [14 empty] | No | 14535 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [5 empty] | 170 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
171 | [14 empty] | No | 14706 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [5 empty] | 171 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
172 | [14 empty] | No | 14878 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [5 empty] | 172 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
173 | [14 empty] | No | 15051 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [5 empty] | 173 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
174 | [14 empty] | No | 15225 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [5 empty] | 174 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
175 | [14 empty] | No | 15400 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [5 empty] | 175 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
176 | [14 empty] | No | 15576 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [5 empty] | 176 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
177 | [14 empty] | No | 15753 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [5 empty] | 177 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
178 | [14 empty] | No | 15931 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [5 empty] | 178 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
179 | [14 empty] | No | 16110 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [5 empty] | 179 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
180 | [14 empty] | No | 16290 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [5 empty] | 180 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
181 | [14 empty] | No | 16471 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [5 empty] | 181 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
182 | [14 empty] | No | 16653 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [5 empty] | 182 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
183 | [14 empty] | No | 16836 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [5 empty] | 183 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
184 | [14 empty] | No | 17020 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [5 empty] | 184 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
185 | [14 empty] | No | 17205 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [5 empty] | 185 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
186 | [14 empty] | No | 17391 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [5 empty] | 186 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
187 | [14 empty] | No | 17578 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [5 empty] | 187 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
188 | [14 empty] | No | 17766 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [5 empty] | 188 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
189 | [14 empty] | No | 17955 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [5 empty] | 189 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
190 | [14 empty] | No | 18145 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [5 empty] | 190 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
191 | [14 empty] | No | 18336 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [5 empty] | 191 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
192 | [14 empty] | No | 18528 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [5 empty] | 192 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
193 | [14 empty] | No | 18721 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [5 empty] | 193 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
194 | [14 empty] | No | 18915 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [5 empty] | 194 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
195 | [14 empty] | No | 19110 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [5 empty] | 195 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
196 | [14 empty] | No | 19306 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [5 empty] | 196 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
197 | [14 empty] | No | 19503 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [5 empty] | 197 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
198 | [14 empty] | No | 19701 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [5 empty] | 198 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
199 | [14 empty] | No | 19900 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [5 empty] | 199 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
200 | [14 empty] | No | 20100 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [5 empty] | 200 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
201 | [14 empty] | No | 20301 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [5 empty] | 201 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
202 | [14 empty] | No | 20503 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [5 empty] | 202 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
203 | [14 empty] | No | 20706 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [5 empty] | 203 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
204 | [14 empty] | No | 20910 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [5 empty] | 204 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
205 | [14 empty] | No | 21115 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [5 empty] | 205 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
206 | [14 empty] | No | 21321 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [5 empty] | 206 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
207 | [14 empty] | No | 21528 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [5 empty] | 207 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
208 | [14 empty] | No | 21736 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [5 empty] | 208 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
209 | [14 empty] | No | 21945 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [5 empty] | 209 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
210 | [14 empty] | No | 22155 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [5 empty] | 210 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
211 | [14 empty] | No | 22366 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [5 empty] | 211 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
212 | [14 empty] | No | 22578 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [5 empty] | 212 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
213 | [14 empty] | No | 22791 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [5 empty] | 213 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
214 | [14 empty] | No | 23005 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [5 empty] | 214 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
215 | [14 empty] | No | 23220 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [5 empty] | 215 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
216 | [14 empty] | No | 23436 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [5 empty] | 216 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
217 | [14 empty] | No | 23653 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [5 empty] | 217 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
218 | [14 empty] | No | 23871 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [5 empty] | 218 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
219 | [14 empty] | No | 24090 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [5 empty] | 219 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
220 | [14 empty] | No | 24310 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [5 empty] | 220 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
221 | [14 empty] | No | 24531 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [5 empty] | 221 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
222 | [14 empty] | No | 24753 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [5 empty] | 222 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
223 | [14 empty] | No | 24976 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [5 empty] | 223 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
224 | [14 empty] | No | 25200 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [5 empty] | 224 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
225 | [14 empty] | No | 25425 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [5 empty] | 225 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
226 | [14 empty] | No | 25651 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [5 empty] | 226 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
227 | [14 empty] | No | 25878 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [5 empty] | 227 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
228 | [14 empty] | No | 26106 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [5 empty] | 228 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
229 | [14 empty] | No | 26335 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [5 empty] | 229 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
230 | [14 empty] | No | 26565 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [5 empty] | 230 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
231 | [14 empty] | No | 26796 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [5 empty] | 231 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
232 | [14 empty] | No | 27028 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [5 empty] | 232 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
233 | [14 empty] | No | 27261 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [5 empty] | 233 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
234 | [14 empty] | No | 27495 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [5 empty] | 234 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
235 | [14 empty] | No | 27730 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [5 empty] | 235 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
236 | [14 empty] | No | 27966 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [5 empty] | 236 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
237 | [14 empty] | No | 28203 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [5 empty] | 237 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
238 | [14 empty] | No | 28441 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [5 empty] | 238 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
239 | [14 empty] | No | 28680 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [5 empty] | 239 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
240 | [14 empty] | No | 28920 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [5 empty] | 240 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
241 | [14 empty] | No | 29161 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [5 empty] | 241 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
242 | [14 empty] | No | 29403 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [5 empty] | 242 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
243 | [14 empty] | No | 29646 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [5 empty] | 243 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
244 | [14 empty] | No | 29890 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [5 empty] | 244 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
245 | [14 empty] | No | 30135 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [5 empty] | 245 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
246 | [14 empty] | No | 30381 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [5 empty] | 246 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
247 | [14 empty] | No | 30628 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [5 empty] | 247 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
248 | [14 empty] | No | 30876 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [5 empty] | 248 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
249 | [14 empty] | No | 31125 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [5 empty] | 249 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
250 | [14 empty] | No | 31375 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [5 empty] | 250 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
251 | [14 empty] | No | 31626 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [5 empty] | 251 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
252 | [14 empty] | No | 31878 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [5 empty] | 252 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
253 | [14 empty] | No | 32131 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [5 empty] | 253 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
254 | [14 empty] | No | 32385 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [5 empty] | 254 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
255 | [14 empty] | No | 32640 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [5 empty] | 255 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
256 | [14 empty] | No | 32896 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [5 empty] | 256 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
257 | [14 empty] | No | 33153 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [5 empty] | 257 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
258 | [14 empty] | No | 33411 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [5 empty] | 258 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
259 | [14 empty] | No | 33670 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [5 empty] | 259 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
260 | [14 empty] | No | 33930 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [5 empty] | 260 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
261 | [14 empty] | No | 34191 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [5 empty] | 261 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
262 | [14 empty] | No | 34453 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [5 empty] | 262 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
263 | [14 empty] | No | 34716 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [5 empty] | 263 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
264 | [14 empty] | No | 34980 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [5 empty] | 264 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
265 | [14 empty] | No | 35245 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [5 empty] | 265 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
266 | [14 empty] | No | 35511 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [5 empty] | 266 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
267 | [14 empty] | No | 35778 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [5 empty] | 267 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
268 | [14 empty] | No | 36046 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [5 empty] | 268 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
269 | [14 empty] | No | 36315 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [5 empty] | 269 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
270 | [14 empty] | No | 36585 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [5 empty] | 270 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
271 | [14 empty] | No | 36856 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [5 empty] | 271 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
272 | [14 empty] | No | 37128 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [5 empty] | 272 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
273 | [14 empty] | No | 37401 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [5 empty] | 273 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
274 | [14 empty] | No | 37675 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [5 empty] | 274 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
275 | [14 empty] | No | 37950 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [5 empty] | 275 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
276 | [14 empty] | No | 38226 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [5 empty] | 276 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
277 | [14 empty] | No | 38503 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [5 empty] | 277 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
278 | [14 empty] | No | 38781 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [5 empty] | 278 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
279 | [14 empty] | No | 39060 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [5 empty] | 279 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
280 | [14 empty] | No | 39340 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [5 empty] | 280 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
281 | [14 empty] | No | 39621 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [5 empty] | 281 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
282 | [14 empty] | No | 39903 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [5 empty] | 282 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
283 | [14 empty] | No | 40186 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [5 empty] | 283 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
284 | [14 empty] | No | 40470 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [5 empty] | 284 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
285 | [14 empty] | No | 40755 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [5 empty] | 285 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
286 | [14 empty] | No | 41041 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [5 empty] | 286 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
287 | [14 empty] | No | 41328 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [5 empty] | 287 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
288 | [14 empty] | No | 41616 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [5 empty] | 288 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
289 | [14 empty] | No | 41905 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [5 empty] | 289 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
290 | [14 empty] | No | 42195 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [5 empty] | 290 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
291 | [14 empty] | No | 42486 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [5 empty] | 291 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
292 | [14 empty] | No | 42778 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [5 empty] | 292 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
293 | [14 empty] | No | 43071 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [5 empty] | 293 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
294 | [14 empty] | No | 43365 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [5 empty] | 294 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
295 | [14 empty] | No | 43660 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [5 empty] | 295 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
296 | [14 empty] | No | 43956 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [5 empty] | 296 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
297 | [14 empty] | No | 44253 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [5 empty] | 297 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
298 | [14 empty] | No | 44551 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [5 empty] | 298 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
299 | [14 empty] | No | 44850 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [5 empty] | 299 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
300 | [14 empty] | No | 45150 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [5 empty] | 300 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!