## GWC Plan
Item | Detail | Estimation (days)
Patient List Screen | Enhancements and changes to Patient List screen | 1
Profile Overview | Profile Overview (Patient Dashboard) | 4
Patient Details | Edit of details as on registration page, also make this available to the patient user | 1
Doctors Notes | Doctors Note Tab - add/edit/remove and print | 1
Exam Notes | Exam Notes Tab - add/edit/remove and print | 0.5
Profile Listings | Listings Management | 1.5
Profile Xrays | Management of Xrays, and Xray types | 2
Profile Scans | Management of Scans - same as Xrays | 0.5
Profile Calendar | Calendar filtered for specific patient | 2 | (Very rough estimate on this one as not sure of the outcome from existing Calendar code)
Profile Adjustments | Adjustments list and management of Adjustments | 2
Profile Subjectives | Subjectives Chart and list | 1.5
Profile Complaints | Profile Complaints Management | 2
Profile History | Profile History Management | 1
Patient Signs and Subjectives | Development of Patient Sign and Subjectives section with queing system | 2
Total Days |  | 21